## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Nalhati-I | Bolpur Mechanical | MAJHKALITHA PIPED WATER SUPPLY SCHEME. | SM/12838 | New | Providing Electro-mechanical accessories and others for Majhkalitha PWSS at Nalhati - I Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000909/2023-2024 | 3539/BOL.MD | 30/11/2023 | 29/01/2024 | RUBY ENTERPRISE | 29.28 | 0 | 0 | 0
2 | BIRBHUM | Nalhati-I | Birbhum Division | MAJHKALITHA PIPED WATER SUPPLY SCHEME. | SM/12838 | New | Material Requisition To Resource Division |  |  | RTOR000015/2023-2024 | 1431/BHM | 25/04/2023 | 25/04/2023 | Resource Division | 13.69 | 0 | 0 | 0
3 | BIRBHUM | Nalhati-I | Bolpur Mechanical | MAJHKALITHA PIPED WATER SUPPLY SCHEME. | SM/12838 | New | WBSEDCL QUOTATION FOR MAJHKALITHA PUMP HOUSE NO-I |  |  | BILL/02130/2023-2024 | BP-2023-24-293 | 07/03/2024 | 07/03/2024 | WBSEDCL | 2.08 | 0 | 0 | 0
4 | BIRBHUM | Nalhati-I | Bolpur Mechanical | MAJHKALITHA PIPED WATER SUPPLY SCHEME. | SM/12838 | New | WBSEDCL QUOTATION FOR MAJHKALITHA P H NO.I WS SCHEME |  |  | BILL/01784/2023-2024 | BP-23-24-246 | 29/01/2024 | 29/01/2024 | WBSEDCL | 3.91 | 0 | 0 | 0
5 | BIRBHUM | Nalhati-I | Bolpur Mechanical | MAJHKALITHA PIPED WATER SUPPLY SCHEME. | SM/12838 | New | WBSEDCL QUOTATION FOR MAJHKALITHA P H NO 2 |  |  | BILL/01709/2023-2024 | BP-23-24-161 | 29/01/2024 | 29/01/2024 | WBSEDCL | 0.23 | 0 | 0 | 0
6 | BIRBHUM | Nalhati-I | Birbhum Division | MAJHKALITHA PIPED WATER SUPPLY SCHEME. | SM/12838 | New | Different works related to water supply scheme at Majhkaltia, Sahira & KANAPIUR PWSS & its adjoining mouzas water supply scheme within Nalhati I Block including supply of all labour & materials under BIRBHUM Division, PHE Dte | AE | JE2 | ORD/000075/2023-2024 | 1348/BHM | 20/04/2023 | 02/08/2025 | M/S GOUTAM DAS | 1594.34 | 0 | 0 | 28
7 | BIRBHUM | Nalhati-I | Birbhum Division | MAJHKALITHA PIPED WATER SUPPLY SCHEME. | SM/12838 | New | Restoration of Roads, pucca drain including Jack pushing & Augur boring along with extension of pipeline (DI & HDPE) with FHTC and supply of sluice valve with construction of valve chamber for Mathkalitha piped Water Supply Scheme under Nalhati Sub Division within Birbhum Division P.H.E. Dte. | AE | JE2 | ORD/000047/2025-2026 | 1508/BHM | 23/05/2025 | 21/08/2025 | M/S GOUTAM DAS | 70.96 | 0 | 0 | 10
Total | [13 empty] | 1714.49 | 0 | 0