## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Murarai-I | Birbhum Division | KAHINAGAR PIPED WATER SUPPLY SCHME | SM/12887 | New | Different works related to water supply scheme at Dalima, Kahinagar & Dumurgram and its adjoining mouzas water supply scheme within MURARAI-I Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE | JE3 | ORD/000080/2023-2024 | 1423/BHM | 25/04/2023 | 19/04/2026 | AKASH CONSTRUCTION | 1377.29 | 2.82 | 0.2 | 16
2 | BIRBHUM | Murarai-I | Bolpur Mechanical | KAHINAGAR PIPED WATER SUPPLY SCHME | SM/12887 | New | Providing Electro-mechanical accessories and others for Kahinagar PWSS at Murarai - I Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000868/2023-2024 | 3286/BOL.MD | 29/09/2023 | 28/11/2023 | MASSK ENGINEERING WORKS | 27.62 | 0 | 0 | 0
3 | BIRBHUM | Murarai-I | Birbhum Division | KAHINAGAR PIPED WATER SUPPLY SCHME | SM/12887 | New | Material Requisition To Resource Division |  |  | RTOR000019/2023-2024 | 1434/BHM | 25/04/2023 | 25/04/2023 | Resource Division | 9.84 | 0 | 0 | 0
4 | BIRBHUM | Murarai-I | Bolpur Mechanical | KAHINAGAR PIPED WATER SUPPLY SCHME | SM/12887 | New | Providing Electro-mechanical accessories and others at Pump House- I & II for Bahadurpur W/S Scheme (Kahinagar PWSS) at Murarai -I Block under Bolpur Mechanical Division PHE Dte | Assistant Engineer | Junior Engineer | ORD/001168/2024-2025 | 464/BOL.MD | 07/03/2025 | 06/04/2025 | SUNIL RABIDAS | 5.5 | 0 | 0 | 0
Total | [13 empty] | 1420.26 | 2.82 | 0.2