## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Mohammad Bazar | Birbhum Division | RAUTARA PIPED WATER SUPPLY SCHEME. | SM/12888 | New | Material Requisition To Resource Division |  |  | RTOR000029/2023-2024 | 1565/BHM | 26/04/2023 | 26/04/2023 | Resource Division | 5.78 | 0 | 0 | 0
2 | BIRBHUM | Mohammad Bazar | Bolpur Mechanical | RAUTARA PIPED WATER SUPPLY SCHEME. | SM/12888 | New | WBSEDCL QUOTATION BILL FOR RAUTARA WS SCHEME P.H.NO.I |  |  | BILL/01151/2023-2024 | BP-23-24-95 | 26/09/2023 | 26/09/2023 | WBSEDCL | 4.22 | 0 | 0 | 0
3 | BIRBHUM | Mohammad Bazar | Bolpur Mechanical | RAUTARA PIPED WATER SUPPLY SCHEME. | SM/12888 | New | WBSEDCL QUOTATION FOR RAUTARA WS SCHEME P H .NO.2 |  |  | BILL/01486/2023-2024 | BP-23-24-197 | 19/12/2023 | 19/12/2023 | WBSEDCL | 4.53 | 0 | 0 | 0
4 | BIRBHUM | Mohammad Bazar | Birbhum Division | RAUTARA PIPED WATER SUPPLY SCHEME. | SM/12888 | New | Different works related to water supply scheme at RAUTARA & its adjoining mouzas water supply scheme within MD BAZAR Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE(HQ) | JE | ORD/000567/2022-2023 | 900/BHM | 22/03/2023 | 01/03/2025 | M/S.KHAN CHOWDHURY BROTHERS AND CO. | 216.16 | 98.35 | 45.5 | 80
5 | BIRBHUM | Mohammad Bazar | Bolpur Mechanical | RAUTARA PIPED WATER SUPPLY SCHEME. | SM/12888 | New | Providing Electro-mechanical accessories and others for Rautara PWSS at Md. Bazar Block under Bolpur Mechanical Division PHE Dte. | Driller in Charge | Junior Engineer | ORD/000290/2023-2024 | 1496/Bol.MD | 17/07/2023 | 03/12/2025 | M/S SWAPAN BANERJEE | 27.11 | 20.82 | 76.82 | 80
Total | [13 empty] | 257.8 | 119.17 | 46.23