## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Suri-II | Birbhum Division | BANSANKHA PIPED WATER SUPPLY SCHEME. | SM/12889 | New | Material Requisition To Resource Division |  |  | RTOR000042/2022-2023 | 1385/BHM | 24/04/2023 | 24/04/2023 | Resource Division | 6.68 | 0 | 0 | 0
2 | BIRBHUM | Suri-II | Bolpur Mechanical | BANSANKHA PIPED WATER SUPPLY SCHEME. | SM/12889 | New | New service connection at Bansankha PH-I W/S scheme Block-Suri II under Bolpur Mechanical Division,PHE Dte. |  |  | BILL/00126/2024-2025 | BP-2024-2025-57 | 05/06/2024 | 05/06/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 7 | 0 | 0 | 0
3 | BIRBHUM | Suri-II | Bolpur Mechanical | BANSANKHA PIPED WATER SUPPLY SCHEME. | SM/12889 | New | New service connection at Bansankha PH-II W/S scheme Block-Suri II under Bolpur Mechanical Division,PHE Dte. |  |  | BILL/00131/2024-2025 | BP-2024-2025-58 | 05/06/2024 | 05/06/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 11.74 | 0 | 0 | 0
4 | BIRBHUM | Suri-II | Birbhum Division | BANSANKHA PIPED WATER SUPPLY SCHEME. | SM/12889 | New | Different works related to water supply scheme at BANSHANKA & HATIKARA its adjoining mouzas water supply scheme within SURI - II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE | JE | ORD/000038/2023-2024 | 1181/BHM | 12/04/2023 | 16/02/2026 | MAHAVIR PUMPS MFG PVT LTD | 773.9 | 0 | 0 | 5
5 | BIRBHUM | Suri-II | Bolpur Mechanical | BANSANKHA PIPED WATER SUPPLY SCHEME. | SM/12889 | New | Providing Electro-mechanical accessories and others for Banshanka & Adjoining moujas water supply scheme at Suri -II Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000885/2023-2024 | 3361/Bol.MD | 10/10/2023 | 09/12/2023 | M/S. S.S. ENTERPRISE | 27.27 | 0 | 0 | 45
Total | [13 empty] | 826.59 | 0 | 0