## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Suri-II | Birbhum Division | SEHANA PIPED WATER SUPPLY SCHEME. | SM/12890 | New | Material Requisition To Resource Division |  |  | RTOR000041/2022-2023 | 1388/BHM | 24/04/2023 | 24/04/2023 | Resource Division | 27.21 | 0 | 0 | 0
2 | BIRBHUM | Suri-II | Bolpur Mechanical | SEHANA PIPED WATER SUPPLY SCHEME. | SM/12890 | New | New service connection at Sehana PH-II, Suri-II Block |  |  | BILL/00125/2024-2025 | BP-2024-2025-66 | 05/06/2024 | 05/06/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 7.59 | 0 | 0 | 0
3 | BIRBHUM | Suri-II | Bolpur Mechanical | SEHANA PIPED WATER SUPPLY SCHEME. | SM/12890 | New | New service connection at Sehana PH-I PWSS, under Suri-II Block. |  |  | BILL/00124/2024-2025 | BP-2024-2025-65 | 05/06/2024 | 05/06/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.87 | 0 | 0 | 0
4 | BIRBHUM | Suri-II | Birbhum Division | SEHANA PIPED WATER SUPPLY SCHEME. | SM/12890 | New | Different works for KASHERHAT & Sehana and its adjoining mouzas water supply scheme within SURI-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE | JE | ORD/000383/2023-2024 | 4138/BHM | 18/10/2023 | 01/01/2026 | PASCON | 975.41 | 0 | 0 | 60
5 | BIRBHUM | Suri-II | Bolpur Mechanical | SEHANA PIPED WATER SUPPLY SCHEME. | SM/12890 | New | Providing Electro-mechanical accessories and others for Sehana PWSS at Suri - II Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer (HQ),Assistant Engineer-III | Junior Engineer | ORD/000434/2023-2024 | 2106/BOL.MD. | 22/08/2023 | 30/06/2025 | STANDARD ELECTRICALS | 28.52 | 0 | 0 | 100
Total | [13 empty] | 1042.59 | 0 | 0