## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Sainthia | Birbhum Division | Jashoda Piped Water Supply Scheme. | SM/12891 | New | Material Requisition To Resource Division |  |  | RTOR000049/2022-2023 | 1378/BHM | 24/04/2023 |  | Resource Division | 47.2 | 0 | 0 | 0
2 | BIRBHUM | Sainthia | Central Drilling | Jashoda Piped Water Supply Scheme. | SM/12891 | New | Supply & Delivery of Consumables with other works at site for construction of Tube Well in Jashoda PWSS , TW-I, Sainthia Block, Birbhum District under CDD, PHE Dte. |  |  | ORD/000464/2022-2023 | 391/CMSD-I | 05/08/2022 | 20/08/2022 | C.M. ENTERPRISE | 2.66 | 2.21 | 83.1 | 100
3 | BIRBHUM | Sainthia | Central Drilling | Jashoda Piped Water Supply Scheme. | SM/12891 | New | Providing drilling crews for construction of Tube Well by departmental Rig machine in Jashoda W/S Scheme, TW-I, Sainthia Block, Birbhum District under CDD, PHE Dte. |  |  | ORD/000465/2022-2023 | 397/CMSD-I | 05/08/2022 | 20/08/2022 | C.M. ENTERPRISE | 3.77 | 2.5 | 66.28 | 100
4 | BIRBHUM | Sainthia | Central Drilling | Jashoda Piped Water Supply Scheme. | SM/12891 | New | Providing Tube Well materials, conforming to IS: 12818 2010 with other works at site for construction of Tube Well in Jashoda W/S Scheme, TW-I, Sainthia Block, Birbhum District under CDD, PHE Dte. |  |  | ORD/000463/2022-2023 | 385/CMSD-I | 05/08/2022 | 20/08/2022 | C.M. ENTERPRISE | 4.18 | 3.06 | 73.11 | 100
5 | BIRBHUM | Sainthia | Bolpur Mechanical | Jashoda Piped Water Supply Scheme. | SM/12891 | New | Providing Electro-mechanical accessories and others for Jashoda & Adjoining moujas water supply scheme at Sainthia Block under Bolpur Mechanical Division PHE Dte. | Driller in Charge | Junior Engineer | ORD/000050/2023-2024 | 1057/Bol.MD | 08/06/2023 | 07/08/2023 | SATYAJIT GHOSH | 29 | 21.81 | 75.19 | 70
6 | BIRBHUM | Sainthia | Bolpur Mechanical | Jashoda Piped Water Supply Scheme. | SM/12891 | New | WBSEDCL QUOTATION FOR UTTAR JASHODA P H NO.I WS SCHEME |  |  | BILL/01469/2023-2024 | BP-23-24-195 | 14/12/2023 |  | WBSEDCL | 7.21 | 0 | 0 | 0
7 | BIRBHUM | Sainthia | Bolpur Mechanical | Jashoda Piped Water Supply Scheme. | SM/12891 | New | WBSEDCL QUOTATION FOR UTTAR JASHODA P H NO.I WS SCHEME |  |  | BILL/01469/2023-2024 | BP-23-24-195 | 14/12/2023 |  | WBSEDCL | 7.21 | 0 | 0 | 0
8 | BIRBHUM | Sainthia | Birbhum Division | Jashoda Piped Water Supply Scheme. | SM/12891 | New | Different works related to water supply scheme at DEOASH, JASODA & JIUI and its adjoining mouzas water supply scheme within SAINTHIA Block including supply of all labour & materials under Birbhum Division, PHE Dte. | AE | JE | ORD/000013/2023-2024 | 1194/BHM | 12/04/2023 | 07/01/2024 | M/S. JAN MAHAMMAD | 1367.24 | 0 | 0 | 45
Total | [13 empty] | 1468.46 | 29.57 | 2.01