## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Murarai-II | Birbhum Division | MITRAPUR WATER SUPPLY SCHEME. | SM/12892 | New | Different works related to water supply scheme at MITRAPUR & its adjoining mouzas water supply scheme within MURARAI-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte | AE | JE1 | ORD/000277/2023-2024 | 3597/BHM | 21/08/2023 | 01/09/2025 | SUNIL RABI DAS | 635.29 | 0 | 0 | 55
2 | BIRBHUM | Murarai-II | Bolpur Mechanical | MITRAPUR WATER SUPPLY SCHEME. | SM/12892 | New | Providing Electro-mechanical accessories and others for Mitrapur PWSS at Murarai - II Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer,Driller in Charge | Junior Engineer | ORD/000945/2023-2024 | 3306/BOL.MD | 29/09/2023 | 01/09/2025 | MITRA ENTERPRISE | 30.25 | 4.6 | 15.19 | 80
3 | BIRBHUM | Murarai-II | Birbhum Division | MITRAPUR WATER SUPPLY SCHEME. | SM/12892 | New | Material Requisition To Resource Division |  |  | RTOR000012/2023-2024 | 1432/BHM | 25/04/2023 | 25/04/2023 | Resource Division | 40.94 | 0 | 0 | 0
4 | BIRBHUM | Murarai-II | Birbhum Division | MITRAPUR WATER SUPPLY SCHEME. | SM/12892 | New | Material Requisition To Resource Division |  |  | RTOR000045/2023-2024 | 1496/BHM | 25/04/2023 | 25/04/2023 | Resource Division | 40.94 | 0 | 0 | 0
5 | BIRBHUM | Murarai-II | Birbhum Division | MITRAPUR WATER SUPPLY SCHEME. | SM/12892 | New | Restoration charges for laying of PHE pipeline from Chainage 9.50 KM (Barsliapukur) to 12.24 KM (end point) of Murarai Mitrapur Road under Rampurhat Highrway Sub-Division of Birbhunr Highrvay Division-1. in the District of Bir.bhurn during the year 2024-25 |  |  | BILL/00737/2024-2025 | BP-2024-25-223 | 12/09/2024 | 12/09/2024 | EXECUTIVE ENGINEER BIRBHUM HIGHWAY DIVISION-I P.W (ROADS) DIRECTORATE | 9.82 | 0 | 0 | 0
6 | BIRBHUM | Murarai-II | Bolpur Mechanical | MITRAPUR WATER SUPPLY SCHEME. | SM/12892 | New | Quotation deposit for empowering Mitrapur P/H-I Water Supply Scheme in Paikar CCC under Bolpur Mechanical Division, PHE Dte. |  |  | BILL/00150/2024-2025 | BP-2024-2025-77 | 13/06/2024 | 13/06/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.64 | 0 | 0 | 0
7 | BIRBHUM | Murarai-II | Bolpur Mechanical | MITRAPUR WATER SUPPLY SCHEME. | SM/12892 | New | Quotation deposit for Mitrapur Water Supply Scheme P/H-II in Paikar CCC under Bolpur Mechanical division, PHE Dte. |  |  | BILL/00829/2024-2025 | BP-24-25-179 | 23/09/2024 | 23/09/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 8.82 | 0 | 0 | 0
8 | BIRBHUM | Murarai-II | Birbhum Division | MITRAPUR WATER SUPPLY SCHEME. | SM/12892 | New | Wall writing on smooth wall surface (preferably of Govt. premises/Boundary Wall) by cleaning the surface thoroughly, removing old paint, preparing with one coat good quality exterior primer and Two cost best quality exterior synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc. of multiple color as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Birbhum all completed as per direction of EIC. (Size- 8'-4') 2215 nos. village (2 nos. each) | AE | Estimator,JE | ORD/000492/2024-2025 | 203/BHM | 16/01/2025 | 16/04/2025 | IMAGIN | 67.84 | 0 | 0 | 100
Total | [13 empty] | 837.56 | 4.6 | 0.55