## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Suri-II | Bolpur Mechanical | HATIKRA PIPED WATER SUPPLY SCHEME. | SM/12893 | New | Providing Electro-mechanical accessories and others for Hatikara PWSS at Suri - II Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000432/2023-2024 | 2105/BOL.MD. | 22/08/2023 | 21/10/2023 | HINDOL ROY | 29.37 | 18.98 | 64.63 | 60
2 | BIRBHUM | Suri-II | Birbhum Division | HATIKRA PIPED WATER SUPPLY SCHEME. | SM/12893 | New | Material Requisition To Resource Division |  |  | RTOR000043/2022-2023 | 1386/BHM | 24/04/2023 | 24/04/2023 | Resource Division | 19.08 | 0 | 0 | 0
3 | BIRBHUM | Suri-II | Birbhum Division | HATIKRA PIPED WATER SUPPLY SCHEME. | SM/12893 | New | Different works related to water supply scheme at BANSHANKA & HATIKARA its adjoining mouzas water supply scheme within SURI - II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE | JE | ORD/000038/2023-2024 | 1181/BHM | 12/04/2023 | 16/02/2026 | MAHAVIR PUMPS MFG PVT LTD | 773.9 | 73.94 | 9.55 | 5
Total | [13 empty] | 822.35 | 92.92 | 11.3