## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Nalhati-I | Birbhum Division | KOGRAM PIPED WATER SUPPLY SCHEME. | SM/12894 | New | Material Requisition To Resource Division |  |  | RTOR000054/2023-2024 | 1572/BHM | 26/04/2023 | 26/04/2023 | Resource Division | 16.61 | 0 | 0 | 0
2 | BIRBHUM | Nalhati-I | Bolpur Mechanical | KOGRAM PIPED WATER SUPPLY SCHEME. | SM/12894 | New | Providing Electro-mechanical accessories and others for Kogram PWSS at Nalhati - I Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000913/2023-2024 | 3541/BOL.MD | 30/11/2023 | 29/01/2024 | A.S.ENTERPRISE | 27.56 | 21.84 | 79.27 | 50
3 | BIRBHUM | Nalhati-I | Bolpur Mechanical | KOGRAM PIPED WATER SUPPLY SCHEME. | SM/12894 | New | WBSEDCL QUOTATION FOR SKOGRAM WS SCHEME |  |  | BILL/01606/2023-2024 | BP-23-24-236 | 29/01/2024 | 29/01/2024 | WBSEDCL | 2.85 | 0 | 0 | 0
4 | BIRBHUM | Nalhati-I | Birbhum Division | KOGRAM PIPED WATER SUPPLY SCHEME. | SM/12894 | New | Erection of Sign Board (900mm X 600mm) for demarcation of land at various places under Birbhum Division, PHE Dte. | AE,AE(HQ) | Estimator,JE | ORD/000458/2024-2025 | 3608/BHM | 31/12/2024 | 31/03/2025 | IMAGIN | 40.29 | 0 | 0 | 95
5 | BIRBHUM | Nalhati-I | Birbhum Division | KOGRAM PIPED WATER SUPPLY SCHEME. | SM/12894 | New | Jack pushing including Augur boring for extension of pipeline (DI & HDPE ) including supply of sluice valve with construction of valve chember and restoration of Roads, pucca drain for KOGRAM piped Water Supply Scheme (Nalhati-I Block) under Nalhati Sub Division within Birbhum Division P.H.E. Dte. | AE | JE2 | ORD/000454/2024-2025 | 3603/BHM | 31/12/2024 | 30/03/2025 | M/S PROCHESTA ENTERPRISE | 79.6 | 0 | 0 | 99
6 | BIRBHUM | Nalhati-I | Birbhum Division | KOGRAM PIPED WATER SUPPLY SCHEME. | SM/12894 | New | Different works related to water supply scheme at KANIOR, KOGRAM & KUSHIPUR PWSS & its adjoining mouzas water supply scheme within Nalhati I Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE | JE2 | ORD/000596/2022-2023 | 1059/BHM | 31/03/2023 | 01/10/2025 | SK ALIM | 1229.19 | 304.63 | 24.78 | 25
Total | [13 empty] | 1396.09 | 326.47 | 23.38