## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Nalhati-I | Birbhum Division | SARIHA PIPED WATER SUPPLY SCHEME | SM/12900 | New | Material Requisition To Resource Division |  |  | RTOR000170/2023-2024 | 2177/BHM | 23/06/2023 | 23/06/2023 | Resource Division | 14.08 | 0 | 0 | 0
2 | BIRBHUM | Nalhati-I | Birbhum Division | SARIHA PIPED WATER SUPPLY SCHEME | SM/12900 | New | Different works related to water supply scheme at Majhkaltia, Sahira & KANAPIUR PWSS & its adjoining mouzas water supply scheme within Nalhati I Block including supply of all labour & materials under BIRBHUM Division, PHE Dte | AE | JE2 | ORD/000075/2023-2024 | 1348/BHM | 20/04/2023 | 02/08/2025 | M/S GOUTAM DAS | 1594.34 | 0 | 0 | 28
3 | BIRBHUM | Nalhati-I | Bolpur Mechanical | SARIHA PIPED WATER SUPPLY SCHEME | SM/12900 | New | Providing Electro-mechanical accessories and others for Sariha PWSS at Nalhati - I Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000881/2023-2024 | 3366/BOL.MD | 11/10/2023 | 29/06/2025 | T.D.K. ENTERPRISE | 27.35 | 0 | 0 | 40
4 | BIRBHUM | Nalhati-I | Birbhum Division | SARIHA PIPED WATER SUPPLY SCHEME | SM/12900 | New | Restoration of Roads, pucca drain including Jack pushing & Augur boring along with extension of pipeline (DI & HDPE) with FHTC and supply of sluice valve with construction of valve chamber for Sariha piped Water Supply Scheme under Nalhati Sub Division within Birbhum Division P.H.E. Dte. | AE | JE2 | ORD/000048/2025-2026 | 1509/BHM | 23/05/2025 | 21/08/2025 | M/S GOUTAM DAS | 83.28 | 0 | 0 | 10
Total | [13 empty] | 1719.05 | 0 | 0