## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Sainthia | Birbhum Division | PHULUR PIPED WATER SUPPLY SCHEME. | SM/12901 | New | Material Requisition To Resource Division |  |  | RTOR000065/2022-2023 | 1416/BHM | 24/04/2023 | 24/04/2023 | Resource Division | 24.19 | 0 | 0 | 0
2 | BIRBHUM | Sainthia | Bolpur Mechanical | PHULUR PIPED WATER SUPPLY SCHEME. | SM/12901 | New | Providing Electro-mechanical accessories and others for Phulur & Adjoining moujas water supply scheme at Sainthia Block under Bolpur Mechanical Division PHE Dte. | Driller in Charge | Junior Engineer | ORD/000413/2023-2024 | 2085/Bol.MD | 22/08/2023 | 05/10/2024 | MASSK ENGINEERING WORKS | 28.91 | 18.02 | 62.32 | 55
3 | BIRBHUM | Sainthia | Bolpur Mechanical | PHULUR PIPED WATER SUPPLY SCHEME. | SM/12901 | New | Quotation deposit for Phulur Water Supply Scheme P/H-II in Sainthia CCC under Bolpur Mechanical division, PHE Dte |  |  | BILL/01087/2024-2025 | BP-24-25-284 | 17/12/2024 | 17/12/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.36 | 0 | 0 | 0
4 | BIRBHUM | Sainthia | Bolpur Mechanical | PHULUR PIPED WATER SUPPLY SCHEME. | SM/12901 | New | WBSEDCL QUIOTATION FOR PHULUR PH NO-I |  |  | BILL/01849/2023-2024 | BP-23-24-275 | 15/02/2024 | 15/02/2024 | WBSEDCL | 0.53 | 0 | 0 | 0
5 | BIRBHUM | Sainthia | Birbhum Division | PHULUR PIPED WATER SUPPLY SCHEME. | SM/12901 | New | Different works related to water supply scheme at PASCHIM NAOPARA, PHULUR & PURBA SIUR its adjoining mouzas water supply scheme within SAINTHIA Block under Birbhum Division, PHE Dte. | AE | JE | ORD/000189/2023-2024 | 2262/BHM | 12/07/2023 | 31/03/2026 | B RAI CONSTRUCTION COMPANY | 1402.44 | 72.4 | 5.16 | 45
Total | [13 empty] | 1460.43 | 90.42 | 6.19