## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Sainthia | Birbhum Division | JIUI PIPED WATER SUPPLY SCHEME. | SM/12902 | New | Material Requisition To Resource Division |  |  | RTOR000050/2022-2023 | 1367/BHM | 24/04/2023 | 24/04/2023 | Resource Division | 17.14 | 0 | 0 | 0
2 | BIRBHUM | Sainthia | Bolpur Mechanical | JIUI PIPED WATER SUPPLY SCHEME. | SM/12902 | New | Providing Electro-mechanical accessories and others for Jiui & Adjoining moujas water supply scheme at Sainthia Block under Bolpur Mechanical Division PHE Dte. | Driller in Charge | Junior Engineer | ORD/000415/2023-2024 | 2087/Bol.MD | 22/08/2023 | 01/07/2025 | M/S. YOUTH ENGINEERS' ENTERPRISE | 28.76 | 13.36 | 46.46 | 50
3 | BIRBHUM | Sainthia | Bolpur Mechanical | JIUI PIPED WATER SUPPLY SCHEME. | SM/12902 | New | WBSEDCL QUIOTATION FOR JIUI PH NO-II |  |  | BILL/01850/2023-2024 | BP-23-24-276 | 15/02/2024 | 15/02/2024 | WBSEDCL | 5 | 0 | 0 | 0
4 | BIRBHUM | Sainthia | Bolpur Mechanical | JIUI PIPED WATER SUPPLY SCHEME. | SM/12902 | New | WBSEDCL QUOTATION FOR JIUI PH I WS SCHEME |  |  | BILL/02134/2023-2024 | BP-2023-24-295 | 12/03/2024 | 12/03/2024 | WBSEDCL | 3.79 | 0 | 0 | 0
5 | BIRBHUM | Sainthia | Birbhum Division | JIUI PIPED WATER SUPPLY SCHEME. | SM/12902 | New | Different works related to water supply scheme at DEOASH, JASODA & JIUI and its adjoining mouzas water supply scheme within SAINTHIA Block including supply of all labour & materials under Birbhum Division, PHE Dte. | AE | JE,JE1 | ORD/000013/2023-2024 | 1194/BHM | 12/04/2023 | 12/06/2025 | M/S. JAN MAHAMMAD | 1367.24 | 157.91 | 11.55 | 75
Total | [13 empty] | 1421.93 | 171.27 | 12.05