## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Dubrajpur | Birbhum Division | Naoadangal and Adjoining Mouzas PWSS | SM/12904 | New | Material Requisition To Resource Division |  |  | RTOR000083/2022-2023 | 1400/BHM | 24/04/2023 | 24/04/2023 | Resource Division | 240.3 | 0 | 0 | 0
2 | BIRBHUM | Dubrajpur | Birbhum Division | Naoadangal and Adjoining Mouzas PWSS | SM/12904 | New | Material Requisition To Resource Division |  |  | RTOR000189/2023-2024 | 3278/BHM | 27/07/2023 | 27/07/2023 | Resource Division | 5.69 | 0 | 0 | 0
3 | BIRBHUM | Dubrajpur | Birbhum Division | Naoadangal and Adjoining Mouzas PWSS | SM/12904 | New | Material Requisition To Resource Division |  |  | RTOR000178/2023-2024 | 2171/BHM | 23/06/2023 | 23/06/2023 | Resource Division | 3.42 | 0 | 0 | 0
4 | BIRBHUM | Dubrajpur | Birbhum Division | Naoadangal and Adjoining Mouzas PWSS | SM/12904 | New | Different works related to water supply scheme at NAOADANGAL & its adjoining mouzas water supply scheme within DUBRAJPUR Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE | JE | ORD/000579/2022-2023 | 935/BHM | 23/03/2023 | 23/12/2023 | SYED KHORSED ALAM | 434.91 | 161.13 | 37.05 | 15
5 | BIRBHUM | Dubrajpur | Bolpur Mechanical | Naoadangal and Adjoining Mouzas PWSS | SM/12904 | New | Providing Electro-mechanical accessories and others for Naoadangal & Adjoining moujas water supply scheme at Dubrajpur Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000365/2023-2024 | 1842/Bol.MD | 01/08/2023 | 30/10/2023 | ORIENTAL ENGINEERING CO. | 54.58 | 29.86 | 54.7 | 50
6 | BIRBHUM | Dubrajpur | Bolpur Mechanical | Naoadangal and Adjoining Mouzas PWSS | SM/12904 | New | Hiring of vehicle for the office of the Executive Engineer, Bolpur Mechanical Division, PHE Dte |  | Junior Engineer | ORD/001048/2023-2024 | ..1299/Bol.MD | 28/06/2023 | 29/10/2023 | SATYAJIT GHOSH | 1.58 | 1.47 | 92.85 | 100
7 | BIRBHUM | Dubrajpur | Bolpur Mechanical | Naoadangal and Adjoining Mouzas PWSS | SM/12904 | New | WBSEDCL QUOTATION FOR NAOADANGAL |  |  | BILL/01576/2023-2024 | BP-23-24-204 | 04/01/2024 | 04/01/2024 | WBSEDCL | 8.4 | 0 | 0 | 0
8 | BIRBHUM | Dubrajpur | Bolpur Mechanical | Naoadangal and Adjoining Mouzas PWSS | SM/12904 | New | Supply, Delivery and Installation of 1 M.T. HOT crane at High Lift Pump House of Noadangal water supply scheme under Bolpur Mechanical Division, PHE. Dte | Assistant Engineer-III | Junior Engineer | ORD/001237/2023-2024 | 537/BOL.MD | 14/03/2024 | 01/04/2025 | ORIENTAL ENGINEERING CO. | 8.48 | 0 | 0 | 100
9 | BIRBHUM | Dubrajpur | Bolpur Mechanical | Naoadangal and Adjoining Mouzas PWSS | SM/12904 | New | Supplementary quotation for installation of one no 63 KVA DTR to effect NSC Nowadagal PHE (Khosnagar) APP No -5003961838 |  |  | BILL/01518/2025-2026 |  | 06/11/2025 | 06/11/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.23 | 0 | 0 | 0
Total | [13 empty] | 761.61 | 192.46 | 25.27