## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Sainthia | Birbhum Division | Nohana and Adjoining Mouzas PWSS | SM/12905 | New | Material Requisition To Resource Division |  |  | RTOR000059/2022-2023 | 1412/BHM | 24/04/2023 | 24/04/2023 | Resource Division | 10.86 | 0 | 0 | 0
2 | BIRBHUM | Sainthia | Birbhum Division | Nohana and Adjoining Mouzas PWSS | SM/12905 | New | Different works related to water supply scheme at NOHANA & its adjoining mouzas water supply scheme within SAINTHIA Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE | JE | ORD/000093/2023-2024 | 1643/BHM | 02/05/2023 | 02/02/2024 | WEIR AND DECK CONSTRUCTION ENGINEERS CO OP SOCIETY LTD | 266.53 | 96.25 | 36.11 | 30
3 | BIRBHUM | Sainthia | Birbhum Division | Nohana and Adjoining Mouzas PWSS | SM/12905 | New | Continuation Work Order for "Preparation & Submission of Detail Project Report (DPR) for NOHANA Piped Water Supply Scheme under command area of Illambazar Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte.". | AE |  | ORD/000775/2022-2023 | 236/BSD | 17/06/2022 | 15/09/2022 | M/S R DUTTA & CO. | 4.99 | 4.6 | 92.21 | 100
4 | BIRBHUM | Sainthia | Bolpur Mechanical | Nohana and Adjoining Mouzas PWSS | SM/12905 | New | New service connection at Nohana and Adjoining Moujas W/S scheme, PH-II, Block-Sainthia under Bolpur Mechanical Division,PHE Dte. |  |  | BILL/00175/2024-2025 | BP-24-25-89 | 19/06/2024 | 19/06/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.29 | 0 | 0 | 0
5 | BIRBHUM | Sainthia | Bolpur Mechanical | Nohana and Adjoining Mouzas PWSS | SM/12905 | New | Quotation for new service connection at Nohana PWSS, P/H- II under Illambazar CCC |  |  | BILL/01020/2024-2025 | BP-24-25-272 | 04/12/2024 | 04/12/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.74 | 0 | 0 | 0
6 | BIRBHUM | Sainthia | Bolpur Mechanical | Nohana and Adjoining Mouzas PWSS | SM/12905 | New | New service connection at Nohana and Adjoining Moujas W/S scheme, PH-I, Block-Sainthia under Bolpur Mechanical Division,PHE Dte. |  |  | BILL/00173/2024-2025 | BP-24-25-88 | 19/06/2024 | 19/06/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.93 | 0 | 0 | 0
7 | BIRBHUM | Sainthia | Bolpur Mechanical | Nohana and Adjoining Mouzas PWSS | SM/12905 | New | Providing Electro-mechanical accessories and others for Nohana & Adjoining moujas water supply scheme at Sainthia Block under Bolpur Mechanical Division PHE Dte. | Driller in Charge | Junior Engineer | ORD/000531/2023-2024 | 2172/Bol.MD | 01/09/2023 | 01/02/2025 | M/S. UTTAM KUMAR CHATTERJEE | 14.97 | 0 | 0 | 80
Total | [13 empty] | 309.31 | 100.85 | 32.61