## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Murarai-I | Birbhum Division | Palsa piped water supply scheme. | SM/12906 | New | Material Requisition To Resource Division |  |  | RTOR000044/2023-2024 | 1441/BHM | 25/04/2023 | 25/04/2023 | Resource Division | 11.75 | 0 | 0 | 0
2 | BIRBHUM | Murarai-I | Bolpur Mechanical | Palsa piped water supply scheme. | SM/12906 | New | Providing Electro-mechanical accessories and others for PALSA piped water supply scheme, Murarai-I block, under Bolpur Mechanical Division PHE Dte. | Driller in Charge | Junior Engineer | ORD/000903/2023-2024 | 3298/Bol.MD | 29/09/2023 | 01/09/2024 | CINZANO | 27.21 | 19.93 | 73.26 | 75
3 | BIRBHUM | Murarai-I | Bolpur Mechanical | Palsa piped water supply scheme. | SM/12906 | New | WBSEDCL QUOTATION MONEY FOR PALSA P H NO.II WS SCHEME |  |  | BILL/01823/2023-2024 | BP-2023-24-258 | 06/02/2024 | 06/02/2024 | WBSEDCL | 3.04 | 0 | 0 | 0
4 | BIRBHUM | Murarai-I | Bolpur Mechanical | Palsa piped water supply scheme. | SM/12906 | New | WBSEDCL QUOTATION FOR PALSA PUMP HOUSE NO I |  |  | BILL/01825/2023-2024 | BP-23-24-257 | 06/02/2024 | 06/02/2024 | WBSEDCL | 3.06 | 0 | 0 | 0
5 | BIRBHUM | Murarai-I | Birbhum Division | Palsa piped water supply scheme. | SM/12906 | New | Different works related to water supply scheme at Palsa & its adjoining mouzas water supply scheme within Murarai-I Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE | JE1 | ORD/000090/2023-2024 | 1639/BHM | 02/05/2023 | 28/08/2026 | GHOSH & BROTHERS DEVCON PRIVATE LIMITED | 290.19 | 87.4 | 30.12 | 30
Total | [13 empty] | 335.24 | 107.33 | 32.02