## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Murarai-I | Bolpur Mechanical | Paniara Piped Water Supply Scheme. | SM/12907 | New | Providing Electro-mechanical accessories and others for PANIARA piped water supply scheme, Murarai-I block, under Bolpur Mechanical Division PHE Dte. | Assistant Engineer,Driller in Charge | Junior Engineer | ORD/000904/2023-2024 | 3299/Bol.MD | 29/09/2023 | 01/04/2025 | M/S. UTTAM KUMAR CHATTERJEE | 26 | 18.91 | 72.71 | 70
2 | BIRBHUM | Murarai-I | Birbhum Division | Paniara Piped Water Supply Scheme. | SM/12907 | New | Material Requisition To Resource Division |  |  | RTOR000034/2023-2024 | 1585/BHM | 26/04/2023 | 26/04/2023 | Resource Division | 8.69 | 0 | 0 | 0
3 | BIRBHUM | Murarai-I | Birbhum Division | Paniara Piped Water Supply Scheme. | SM/12907 | New | Different works related to water supply scheme at PANIARA & its adjoining mouzas water supply scheme within Murarai-I Block including supply of all labour & materials under Birbhum Division, PHE Dte. | AE | JE3 | ORD/000694/2023-2024 | 1040/BHM | 15/03/2024 | 02/09/2026 | ANIRUDDHA FARUQUE | 65.65 | 0 | 0 | 5
Total | [13 empty] | 100.35 | 18.91 | 18.84