## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Murarai-II | Birbhum Division | Simgram Piped Water Supply Scheme. | SM/12908 | New | Material Requisition To Resource Division |  |  | RTOR000103/2023-2024 | 1530/BHM | 26/04/2023 | 26/04/2023 | Resource Division | 10.16 | 0 | 0 | 0
2 | BIRBHUM | Murarai-II | Bolpur Mechanical | Simgram Piped Water Supply Scheme. | SM/12908 | New | Providing Electro-mechanical accessories and others for SIMGRAM piped water supply scheme, Murarai-II block, under Bolpur Mechanical Division PHE Dte. | Driller in Charge | Junior Engineer | ORD/000548/2023-2024 | 2144/Bol.MD | 25/08/2023 | 24/10/2023 | S.G.TECHNICAL SERVICES | 25.67 | 17.44 | 67.94 | 60
3 | BIRBHUM | Murarai-II | Bolpur Mechanical | Simgram Piped Water Supply Scheme. | SM/12908 | New | Quotation deposit for empowering Simgram Water Supply Scheme P/H -II in Paikar CCC under Bolpur Mechanical Division, PHE Dte |  |  | BILL/00114/2024-2025 | BP-2024-2025-53 | 28/05/2024 | 28/05/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.08 | 0 | 0 | 0
4 | BIRBHUM | Murarai-II | Bolpur Mechanical | Simgram Piped Water Supply Scheme. | SM/12908 | New | Quotation deposit for empowering Simgram Water Supply Scheme P/H -I in Paikar CCC under Bolpur Mechanical Division, PHE Dte |  |  | BILL/00091/2024-2025 | BP-2024-2025-42 | 28/05/2024 | 28/05/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.97 | 0 | 0 | 0
5 | BIRBHUM | Murarai-II | Birbhum Division | Simgram Piped Water Supply Scheme. | SM/12908 | New | Different works related to water supply scheme at SIMGRAM & its adjoining mouzas water supply scheme within MURARAI-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE | JE1 | ORD/000100/2023-2024 | 1719/BHM | 12/05/2023 | 16/01/2025 | M/S MD AMINUL ISLAM | 69.99 | 40.44 | 57.78 | 65
Total | [13 empty] | 113.87 | 57.88 | 50.83