## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Suri-I | Birbhum Division | Kachujore Piped Water Supply Scheme. | SM/13016 | New | Material Requisition To Resource Division |  |  | RTOR000036/2022-2023 | 1381/BHM | 24/04/2023 | 24/04/2023 | Resource Division | 9.47 | 0 | 0 | 0
2 | BIRBHUM | Suri-I | Bolpur Mechanical | Kachujore Piped Water Supply Scheme. | SM/13016 | New | Providing Electro-mechanical accessories and others for Kachujor PWSS at Suri -I Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000424/2023-2024 | 2102/BOL.MD. | 22/08/2023 | 01/04/2025 | UNITED TRADERS | 27.62 | 22.36 | 80.98 | 50
3 | BIRBHUM | Suri-I | Bolpur Mechanical | Kachujore Piped Water Supply Scheme. | SM/13016 | New | WBSEDCL QUOTATION FOR KACHUJORE PWSS |  |  | BILL/01787/2023-2024 | BP-23-24-247 | 29/01/2024 | 29/01/2024 | WBSEDCL | 4.01 | 0 | 0 | 0
4 | BIRBHUM | Suri-I | Bolpur Mechanical | Kachujore Piped Water Supply Scheme. | SM/13016 | New | Quotation for new service connection at Kachujore Water Supply Scheme (TW No-II) under Suri-I Block. |  |  | BILL/00070/2024-2025 | BP-2024-2025-31 | 20/05/2024 | 20/05/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.09 | 0 | 0 | 0
5 | BIRBHUM | Suri-I | Birbhum Division | Kachujore Piped Water Supply Scheme. | SM/13016 | New | Different Works for KACHUJOR & its adjoining mouzas water supply scheme within SURI-I Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE | JE1 | ORD/000005/2023-2024 | 1084/BHM | 06/04/2023 | 02/02/2026 | HIRANMAY GHOSH | 149.6 | 62.71 | 41.92 | 35
Total | [13 empty] | 195.8 | 85.08 | 43.45