## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Rampurhat-I | Birbhum Division | Tilai piped water supply scheme. | SM/13127 | New | Material Requisition To Resource Division |  |  | RTOR000101/2023-2024 | 1531/BHM | 26/04/2023 | 26/04/2023 | Resource Division | 13.56 | 0 | 0 | 0
2 | BIRBHUM | Rampurhat-I | Bolpur Mechanical | Tilai piped water supply scheme. | SM/13127 | New | Providing Electro-mechanical accessories and others for Tilai & Adjoining PWSS at Rampurhat - I Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000923/2023-2024 | 3529/Bol.MD | 29/11/2023 | 28/01/2024 | MITRA ENTERPRISE | 26.05 | 20.82 | 79.9 | 30
3 | BIRBHUM | Rampurhat-I | Birbhum Division | Tilai piped water supply scheme. | SM/13127 | New | Material Requisition To Resource Division |  |  | RTOR000040/2024-2025 | 2483/BHM | 03/09/2024 | 03/09/2024 | Resource Division | 7.68 | 0 | 0 | 0
4 | BIRBHUM | Rampurhat-I | Birbhum Division | Tilai piped water supply scheme. | SM/13127 | New | Sinking of 250 X 150 mm Dia tubewell Drilling by Direct Rotary method (Two Nos ), Construction of 5.90 m X 4.10 m Pump room/ Chlorine room with sanitary arrangements, 150 CuM OHR, Boundary wall, Soil Investigation, Land development, Rising main, Laying distribution, road restoration and Providing functional household tap connection related to water supply scheme at Tilai & its adjoining mouzas water supply scheme within RAMPURHAT-I Block including supply of all labour & materials under BIRBHUM Division, PHE Dte | AE | JE,JE2 | ORD/000132/2024-2025 | 2316/BHM | 21/08/2024 | 21/08/2025 | S D CONSTRUCTION | 349.88 | 0 | 0 | 15
5 | BIRBHUM | Rampurhat-I | Bolpur Mechanical | Tilai piped water supply scheme. | SM/13127 | New | Quotation for new service connection at Tilai PWSS PH-II (Kabilpur), Block- Rampurhat-I under Rampuhat CCC |  |  | BILL/00598/2025-2026 |  | 13/06/2025 | 13/06/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 15.27 | 0 | 0 | 0
6 | BIRBHUM | Rampurhat-I | Bolpur Mechanical | Tilai piped water supply scheme. | SM/13127 | New | Quotation for new service connection at Tilai PWSS P/H-I at Block- Rampurhat-I |  |  | BILL/00400/2025-2026 |  | 03/06/2025 | 03/06/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.94 | 0 | 0 | 0
Total | [13 empty] | 415.38 | 20.82 | 5.01