## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Narayanghati Phase-II Water Supply Scheme. | SM/13371 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Narayanghati w/s Scheme in Rampurhat Sub-Division under Birbhum Division, PHE Dte. (Sl. No.-2) | AE | JE1 | ORD/000365/2021-2022 | 1915/BHM | 24/11/2021 | 23/01/2022 | TAPAN KUMAR DATTA | 82.11 | 0 | 0 | 53
2 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Narayanghati Phase-II Water Supply Scheme. | SM/13371 | Retrofitting | Additional FHTC works from existing distribution system at Narayanghati & Bidyadhari habitation under Narayanghati mouzas within Narayanghati w/s Scheme under Rampurhat Sub- Division, P.H.E. Dte. (Sl.No-29) | AE | JE1 | ORD/000203/2022-2023 | 332/RSD | 08/09/2022 | 08/10/2022 | TAPAN KUMAR DATTA | 4.97 | 0 | 0 | 100
3 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Narayanghati Phase-II Water Supply Scheme. | SM/13371 | Retrofitting | Additional FHTC works from existing distribution system at different mouzas ie Bhabaghati, Hatinagar, Mahalas, Bandha, Balur & Akna within Narayanghati w/s Scheme under Rampurhat Sub- Division, P.H.E. Dte.(Sl.No-28) | AE | JE1 | ORD/000202/2022-2023 | 331/RSD | 08/09/2022 | 08/10/2022 | TAPAN KUMAR DATTA | 4.95 | 0 | 0 | 100
4 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Narayanghati Phase-II Water Supply Scheme. | SM/13371 | Retrofitting | Additional FHTC works from existing distribution system at Kalikapur,Kajipara,& Narayanghati habitations under Narayanghati mouza within Narayanghati w/s Scheme under Rampurhat Sub- Division, P.H.E. Dte.(Sl.No-27) | AE | JE1 | ORD/000201/2022-2023 | 330/RSD | 08/09/2022 | 08/10/2022 | TAPAN KUMAR DATTA | 4.98 | 0 | 0 | 100
5 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Narayanghati Phase-II Water Supply Scheme. | SM/13371 | Retrofitting | Providing 01 No. additional FHTC along with allied works from existing distribution system at Narayanghati (Konai Para) Jl. No. 92 under Kundala G.P. within Narayanghati W/S Scheme under Rampurhat Sub- Division, P.H.E. Dte. | AE | JE1 | ORD/000229/2023-2024 | 200/RSD | 28/07/2023 | 04/08/2023 | ASHUTOSH BISWAS | 0.29 | 0 | 0 | 100
Total | [13 empty] | 97.3 | 0 | 0