## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Mayureswar-I | Birbhum Division | Asuralay Piped Water Supply Scheme under mayureswar-I Block within Birbhum Division. | SM/13376 | New | Preparation & Submission of DPR for (Asuralay) Water Supply Scheme under Mayureswar-I Development Block. | AE | JE1 | ORD/000561/2022-2023 | 158/RSD | 18/04/2022 | 17/07/2022 | ENVIROTECH SOLUTIONS | 4.65 | 4.63 | 99.56 | 100
2 | BIRBHUM | Mayureswar-I | Bolpur Mechanical | Asuralay Piped Water Supply Scheme under mayureswar-I Block within Birbhum Division. | SM/13376 | New | Providing Electro-mechanical accessories and others for Asuralaya PWSS at Mayureswar - I Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000727/2023-2024 | 3474/Bol.MD | 07/11/2023 | 20/05/2027 | S. S. ENTERPRISES | 43.56 | 17.02 | 39.07 | 50
3 | BIRBHUM | Mayureswar-I | Birbhum Division | Asuralay Piped Water Supply Scheme under mayureswar-I Block within Birbhum Division. | SM/13376 | New | Material Requisition To Resource Division |  |  | RTOR000121/2023-2024 | 1526/BHM | 26/04/2023 | 26/04/2023 | Resource Division | 17.89 | 0 | 0 | 0
4 | BIRBHUM | Mayureswar-I | Birbhum Division | Asuralay Piped Water Supply Scheme under mayureswar-I Block within Birbhum Division. | SM/13376 | New | Different works related to water supply scheme at BIRCHANDRAPUR, ASURLAYA, BARATURIGRAM & KANAIPUR and its adjoining mouzas water supply scheme within MAYURESWAR-I Block including supply of all labour & materials under Birbhum Division, PHE Dte. (2nd Call) | AE | JE2,JE3 | ORD/000471/2023-2024 | 505/BHM | 05/02/2024 | 30/09/2025 | B RAI CONSTRUCTION COMPANY | 2071.77 | 150.28 | 7.25 | 20
5 | BIRBHUM | Mayureswar-I | Bolpur Mechanical | Asuralay Piped Water Supply Scheme under mayureswar-I Block within Birbhum Division. | SM/13376 | New | Supply and Installation of Submersible pumping machineries and other electromechanical equipments at Asuralaya PWSS under Mayureswar - I Block in the Dist of Birbhum under Bolpur Mechanical Division,P.H.E.Dte. | Assistant Engineer-III | Junior Engineer | ORD/001232/2023-2024 | 518/BOL.MD | 14/03/2024 | 01/11/2025 | M/S. YOUTH ENGINEERS' ENTERPRISE | 7.62 | 5 | 65.7 | 100
6 | BIRBHUM | Mayureswar-I | Bolpur Mechanical | Asuralay Piped Water Supply Scheme under mayureswar-I Block within Birbhum Division. | SM/13376 | New | New service connection at Asuralaya PH-I PWSS under Bolpur Mechanical Division, P.H.E Dte. |  |  | BILL/00839/2024-2025 | BP-24-25-189 | 24/09/2024 | 24/09/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.58 | 0 | 0 | 0
7 | BIRBHUM | Mayureswar-I | Bolpur Mechanical | Asuralay Piped Water Supply Scheme under mayureswar-I Block within Birbhum Division. | SM/13376 | New | Quotation for new service connection at Asuralya PWSS, P.H- II under Mollarpur CCC (Mayureswar-I Block) |  |  | BILL/00958/2024-2025 | BP-2024-2025-25 | 18/11/2024 | 18/11/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.6 | 0 | 0 | 0
8 | BIRBHUM | Mayureswar-I | Bolpur Mechanical | Asuralay Piped Water Supply Scheme under mayureswar-I Block within Birbhum Division. | SM/13376 | New | Providing and Installation of Submersible pumping Machineries at newly sunk Tube Well and allieds works at Khanpur Piped Water Supply Scheme, (Asuralaya PWSS) Block-Dubrajpur under Bolpur Mechanical Division, P.H.E.Dte | Assistant Engineer-III | Junior Engineer | ORD/001169/2024-2025 | 465/BOL.MD | 07/03/2025 | 06/04/2025 | SATYAJIT GHOSH | 8.51 | 0 | 0 | 100
Total | [13 empty] | 2163.18 | 176.93 | 8.18