## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Nanoor | Birbhum Division | BENAGRAM PIPED WATER SUPPLY SCHEME | SM/13377 | New | Continuation Work Order for "Preparation & Submission of Detail Project Report (DPR) for BENAGRAM Piped Water Supply Scheme under Nanoor Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte.". | AE | JE4 | ORD/000645/2022-2023 | 171/BSD | 27/04/2022 | 26/07/2022 | RADIANT | 4 | 3.62 | 90.62 | 100
2 | BIRBHUM | Nanoor | Central Drilling | BENAGRAM PIPED WATER SUPPLY SCHEME | SM/13377 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
3 | BIRBHUM | Nanoor | Birbhum Division | BENAGRAM PIPED WATER SUPPLY SCHEME | SM/13377 | New | Material Requisition To Resource Division |  |  | RTOR000065/2023-2024 | 1469/BHM | 25/04/2023 | 25/04/2023 | Resource Division | 37.92 | 0 | 0 | 0
4 | BIRBHUM | Nanoor | Bolpur Mechanical | BENAGRAM PIPED WATER SUPPLY SCHEME | SM/13377 | New | Construction of Tube Well (300 MM x 200 MM x Depth 450 Mtr) for Benagram WSS (TW No I and II), Block- Nanoor, in Birbhum District under Bolpur Mechanical Division, P.H.E Dte | Assistant Engineer | Junior Engineer | ORD/000961/2024-2025 | 4530/BOL.MD | 20/12/2024 | 19/04/2025 | MENAKA ENTERPRISE | 73 | 0 | 0 | 0
5 | BIRBHUM | Nanoor | Birbhum Division | BENAGRAM PIPED WATER SUPPLY SCHEME | SM/13377 | New | Different works related to water supply scheme at BENAGRAM PIPED WATER SUPPLY SCHEME (TSM/015486) within NANOOR Block including supply of all labour & materials under Bolpur Sub- Division within Birbhum Division, PHE Dte." | Assistant Engineer | JE2 ,JE3 | ORD/000142/2024-2025 | 2428/BHM | 29/08/2024 | 29/08/2025 | M/S. A K ENTERPRISE | 355.96 | 0 | 0 | 0
6 | BIRBHUM | Nanoor | Birbhum Division | BENAGRAM PIPED WATER SUPPLY SCHEME | SM/13377 | New | Material Requisition To Resource Division |  |  | RTOR000038/2024-2025 | 2486/BHM | 03/09/2024 | 03/09/2024 | Resource Division | 8.22 | 0 | 0 | 0
Total | [13 empty] | 21818.86 | 3.62 | 0.02