## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Nanoor | Birbhum Division | BENGA CHATRA PIPED WATER SUPPLY SCHEME | SM/13408 | New | Continuation Work Order for "Preparation & Submission of Detail Project Report (DPR) for BENGACHATRA Piped Water Supply Scheme under Nanoor Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte.". | AE | JE4 | ORD/000641/2022-2023 | 156/BSD | 20/04/2022 | 19/07/2022 | RADIANT | 4.36 | 4.16 | 95.47 | 100
2 | BIRBHUM | Nanoor | Birbhum Division | BENGA CHATRA PIPED WATER SUPPLY SCHEME | SM/13408 | New | Material Requisition To Resource Division |  |  | RTOR000066/2023-2024 | 1523/BHM | 26/04/2023 | 26/04/2023 | Resource Division | 33.24 | 0 | 0 | 0
3 | BIRBHUM | Nanoor | Birbhum Division | BENGA CHATRA PIPED WATER SUPPLY SCHEME | SM/13408 | New | Construction of 200 Cum capacity O.H.R. with soil Investigation, 5.90 m X 4.10 m Pump room/ Chlorine room with sanitary arrangements, laying of Rising Main, Distribution System with FHTC and different works related to BENGA CHATRA PIPED WATER SUPPLY SCHEME (TSM/015476) within NANOOR Block including supply of all labour & materials under Bolpur Sub- Division within Birbhum Division, PHE Dte. | Assistant Engineer | JE2 | ORD/000147/2024-2025 | 2576/BHM | 09/09/2024 | 09/09/2025 | M/S R B ENTERPRISE | 367.97 | 0 | 0 | 0
4 | BIRBHUM | Nanoor | Birbhum Division | BENGA CHATRA PIPED WATER SUPPLY SCHEME | SM/13408 | New | Material Requisition To Resource Division |  |  | RTOR000052/2024-2025 | 3258/BHM | 02/12/2024 | 02/12/2024 | Resource Division | 9.4 | 0 | 0 | 0
5 | BIRBHUM | Nanoor | Bolpur Mechanical | BENGA CHATRA PIPED WATER SUPPLY SCHEME | SM/13408 | New | Construction of Tube Well (300 MM x 200 MM x Depth 450 Mtr) for Benga Chatra & Ramkrishnapur Water supply Scheme, Block- Nanoor, in Birbhum District by Bolpur Mechanical Division, P.H.Engineering Dte. | Assistant Engineer | Junior Engineer | ORD/000969/2024-2025 | 4538/BOL.MD | 20/12/2024 | 19/04/2025 | MENAKA ENTERPRISE | 73.34 | 0 | 0 | 50
6 | BIRBHUM | Nanoor | Birbhum Division | BENGA CHATRA PIPED WATER SUPPLY SCHEME | SM/13408 | New | Erection of Sign Board (900mm X 600mm) for demarcation of land at various places under Birbhum Division, PHE Dte. | AE,AE(HQ) | Estimator,JE | ORD/000458/2024-2025 | 3608/BHM | 31/12/2024 | 31/03/2025 | IMAGIN | 40.29 | 0 | 0 | 95
7 | BIRBHUM | Nanoor | Central Drilling | BENGA CHATRA PIPED WATER SUPPLY SCHEME | SM/13408 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 21.45 | 0.1 | 11
Total | [13 empty] | 21868.37 | 25.62 | 0.12