## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Suri-I | Birbhum Division | PURBA BANKATI PIPED WATER SUPPLY SCHEME. | SM/13470 | New | Material Requisition To Resource Division |  |  | RTOR000038/2022-2023 | 1383/BHM | 24/04/2023 | 24/04/2023 | Resource Division | 8.65 | 0 | 0 | 0
2 | BIRBHUM | Suri-I | Birbhum Division | PURBA BANKATI PIPED WATER SUPPLY SCHEME. | SM/13470 | New | Different Works for PURBA BANKATI & its adjoining mouzas water supply scheme within SURI-I Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. Sl No 03 | AE | JE3 | ORD/000509/2022-2023 | 675/BHM | 01/03/2023 | 30/12/2024 | MUKHERJEE ENTERPRISE | 152.12 | 0 | 0 | 68
3 | BIRBHUM | Suri-I | Bolpur Mechanical | PURBA BANKATI PIPED WATER SUPPLY SCHEME. | SM/13470 | New | WBSEDCL QUOTATION FOR PURBA BANKATI WS SCHEME |  |  | BILL/01786/2023-2024 | BP-23-24-248 | 29/01/2024 | 29/01/2024 | WBSEDCL | 10.18 | 0 | 0 | 0
4 | BIRBHUM | Suri-I | Bolpur Mechanical | PURBA BANKATI PIPED WATER SUPPLY SCHEME. | SM/13470 | New | Providing Electro-mechanical accessories and others for Purba Bankati & Adjoining moujas water supply scheme at Suri - I Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/001105/2023-2024 | 3314/BOL.MD | 29/09/2023 | 30/04/2025 | BENGAL CONSTRUCTION | 19.05 | 0 | 0 | 45
Total | [13 empty] | 190 | 0 | 0