## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Dubrajpur | Birbhum Division | Paratpur Piped Water Supply Scheme. | SM/13474 | New | Different works related to water supply scheme at CHINPAI, LOBA & PARATPUR and its adjoining mouzas water supply scheme within DUBRAJPUR Block including supply of all labour & materials under BIRBHUM Division, PHE Dte | AE | JE1 | ORD/000265/2023-2024 | 3476/BHM | 08/08/2023 | 01/11/2026 | B RAI CONSTRUCTION COMPANY | 2497.19 | 65.66 | 2.63 | 45
2 | BIRBHUM | Dubrajpur | Bolpur Mechanical | Paratpur Piped Water Supply Scheme. | SM/13474 | New | Providing Electro-mechanical accessories and others for Paratpur & Adjoining moujas water supply scheme at Dubrajpur Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000937/2023-2024 | 3394/Bol.MD | 17/10/2023 | 15/01/2024 | EASTERN INDIA SALES & SERVICE | 79.72 | 0 | 0 | 0
3 | BIRBHUM | Dubrajpur | Birbhum Division | Paratpur Piped Water Supply Scheme. | SM/13474 | New | Material Requisition To Resource Division |  |  | RTOR000073/2022-2023 | 1401/BHM | 24/04/2023 | 24/04/2023 | Resource Division | 70.19 | 0 | 0 | 0
4 | BIRBHUM | Dubrajpur | Birbhum Division | Paratpur Piped Water Supply Scheme. | SM/13474 | New | Material Requisition To Resource Division |  |  | RTOR000187/2023-2024 | 3279/BHM | 27/07/2023 | 27/07/2023 | Resource Division | 2.05 | 0 | 0 | 0
Total | [13 empty] | 2649.15 | 65.66 | 2.48