## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Mayureswar-I | Bolpur Mechanical | Bhagabatipur Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division. | SM/13475 | New | Providing Electro-mechanical accessories and others for Bhagabatipur PWSS at Mayureswar - I Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000348/2023-2024 | 1746/Bol.MD | 27/07/2023 | 25/09/2023 | P. K. ENGINEERING | 43.95 | 0 | 0 | 30
2 | BIRBHUM | Mayureswar-I | Birbhum Division | Bhagabatipur Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division. | SM/13475 | New | Continuation Work Order for Preparation & Submission of DPR for (Bhagabatipur) Water Supply Scheme under Mayureswar-I Development Block | AE | JE1 | ORD/000621/2022-2023 | 202/RSD | 08/06/2022 | 06/09/2022 | ENVIROTECH SOLUTIONS | 2.86 | 0 | 0 | 100
3 | BIRBHUM | Mayureswar-I | Birbhum Division | Bhagabatipur Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division. | SM/13475 | New | Material Requisition To Resource Division |  |  | RTOR000114/2023-2024 | 1506/BHM | 25/04/2023 | 25/04/2023 | Resource Division | 10.66 | 0 | 0 | 0
4 | BIRBHUM | Mayureswar-I | Bolpur Mechanical | Bhagabatipur Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division. | SM/13475 | New | WBSEDCL QUOTATION MONEY FOR BHAGABATIPUR WS SCHEME |  |  | BILL/00722/2023-2024 | BP-2023-2024-76 | 24/08/2023 | 24/08/2023 | WBSEDCL | 3.28 | 0 | 0 | 0
5 | BIRBHUM | Mayureswar-I | Bolpur Mechanical | Bhagabatipur Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division. | SM/13475 | New | WBSEDCL QUOTATION FOR BHAGABATIPUR WS SCHEME |  |  | BILL/01241/2023-2024 | BP-23-24-121 | 12/10/2023 | 12/10/2023 | WBSEDCL | 3.64 | 0 | 0 | 0
6 | BIRBHUM | Mayureswar-I | Bolpur Mechanical | Bhagabatipur Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division. | SM/13475 | New | Supply and Delivery of Pumping Machinery for Bhagabatipur water supply scheme Block Mayureswar ¿I under Bolpur Mechanical Division PHE. Dte. | Assistant Engineer-III | Junior Engineer | ORD/001317/2023-2024 | 607/AE-III | 27/03/2024 | 03/04/2024 | P. K. ENGINEERING | 1.49 | 0 | 0 | 100
7 | BIRBHUM | Mayureswar-I | Birbhum Division | Bhagabatipur Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division. | SM/13475 | New | Material Requisition To Resource Division |  |  | RTOR000202/2023-2024 | 209/BHM | 22/01/2024 | 22/01/2024 | Resource Division | 3.34 | 0 | 0 | 0
8 | BIRBHUM | Mayureswar-I | Bolpur Mechanical | Bhagabatipur Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division. | SM/13475 | New | WBSEDCL QUOTATION FOR BHAGABATIPUR PUMP HOUSE NO-II |  |  | BILL/02078/2023-2024 | BP-2023-24-289 | 04/03/2024 | 04/03/2024 | WBSEDCL | 0.9 | 0 | 0 | 0
9 | BIRBHUM | Mayureswar-I | Birbhum Division | Bhagabatipur Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division. | SM/13475 | New | Different works related to water supply scheme at BHAGABATIPUR & its adjoining mouzas water supply scheme within MAYURESWAR-I Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE | JE,JE1 | ORD/000003/2023-2024 | 1082/BHM | 06/04/2023 | 01/01/2025 | ZEBA CONSTRUCTION | 253.52 | 0 | 0 | 100
Total | [13 empty] | 323.64 | 0 | 0