## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Mayureswar-I | Bolpur Mechanical | Shibgram Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division. | SM/13476 | New | Providing Electro-mechanical accessories and others for Shibgram PWSS at Mayureswar - I Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000726/2023-2024 | 3473/Bol.MD | 07/11/2023 | 06/01/2024 | R. N. S. TRADING | 44.5 | 0 | 0 | 0
2 | BIRBHUM | Mayureswar-I | Birbhum Division | Shibgram Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division. | SM/13476 | New | Continuation Work Order for Preparation & Submission of DPR for (Shibgram) Water Supply Scheme under Mayureswar-I Development Block. | AE | JE1 | ORD/000635/2022-2023 | 244/RSD | 14/07/2022 | 12/10/2022 | ENVIROTECH SOLUTIONS | 4.65 | 0 | 0 | 100
3 | BIRBHUM | Mayureswar-I | Birbhum Division | Shibgram Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division. | SM/13476 | New | Material Requisition To Resource Division |  |  | RTOR000075/2023-2024 | 1522/BHM | 26/04/2023 | 26/04/2023 | Resource Division | 10.37 | 0 | 0 | 0
4 | BIRBHUM | Mayureswar-I | Birbhum Division | Shibgram Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division. | SM/13476 | New | Material Requisition To Resource Division |  |  | RTOR000205/2023-2024 | 198/BHM | 22/01/2024 | 22/01/2024 | Resource Division | 4 | 0 | 0 | 0
5 | BIRBHUM | Mayureswar-I | Bolpur Mechanical | Shibgram Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division. | SM/13476 | New | Quotation For new connection at Shibgram PWSS P/H-1 (block -Mayureswar -I) |  |  | BILL/00080/2024-2025 | BP-2024-2025-30 | 28/05/2024 | 28/05/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.21 | 0 | 0 | 0
6 | BIRBHUM | Mayureswar-I | Bolpur Mechanical | Shibgram Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division. | SM/13476 | New | New service connection at Shibgram PH-II under Mayureswar -I block. |  |  | BILL/00073/2024-2025 | BP-2024-2025-29 | 28/05/2024 | 28/05/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.84 | 0 | 0 | 0
7 | BIRBHUM | Mayureswar-I | Birbhum Division | Shibgram Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division. | SM/13476 | New | Different works related to water supply scheme at LACHHIATOR, DAKSHINGRAM, SONJ & SHIBGRAM and its adjoining mouzas water supply scheme within MAYURESWAR-I Block including supply of all labour & materials under Birbhum Division, PHE Dte. | AE | JE2 | ORD/000385/2023-2024 | 4142/BHM | 19/10/2023 | 01/01/2026 | B RAI CONSTRUCTION COMPANY | 2003.84 | 0 | 0 | 60
Total | [13 empty] | 2074.41 | 0 | 0