## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Nanoor | Birbhum Division | FEUGRAM PIPED WATER SUPPLY SCHEME | SM/13477 | New | Preparation & Submission of Detail Project Report (DPR) for FEUGRAM Piped Water Supply Scheme under Nanoor Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte. | AE | JE4 | ORD/001139/2021-2022 | 89/BSD | 10/03/2022 | 08/06/2022 | RADIANT | 4.87 | 4.73 | 97.21 | 100
2 | BIRBHUM | Nanoor | Birbhum Division | FEUGRAM PIPED WATER SUPPLY SCHEME | SM/13477 | New | Material Requisition To Resource Division |  |  | RTOR000061/2023-2024 | 1449/BHM | 25/04/2023 | 25/04/2023 | Resource Division | 24.16 | 0 | 0 | 0
3 | BIRBHUM | Nanoor | Birbhum Division | FEUGRAM PIPED WATER SUPPLY SCHEME | SM/13477 | New | "Construction of 200CuM. capacity O.H.R. with Soil Investigation,5.90 m X 4.10 m Pump room/ Chlorine room with sanitary arrangements.laying of Rising Main,Distribution System with FHTC and different works related to FEUGRAM PIPED WATER SUPPLY SCHEME (TSM/015471) within NANOOR Block including supply of all labour & materials under Bolpur Sub-Division within Birbhum Division, PHE Dte." | Assistant Engineer | JE2 ,JE3 | ORD/000099/2024-2025 | 2115/BHM | 29/07/2024 | 29/07/2025 | BANI ENGINEERING CO. | 483.16 | 0 | 0 | 0
4 | BIRBHUM | Nanoor | Birbhum Division | FEUGRAM PIPED WATER SUPPLY SCHEME | SM/13477 | New | Material Requisition To Resource Division |  |  | RTOR000018/2024-2025 | 2441/BHM | 30/08/2024 | 30/08/2024 | Resource Division | 10.68 | 0 | 0 | 0
5 | BIRBHUM | Nanoor | Bolpur Mechanical | FEUGRAM PIPED WATER SUPPLY SCHEME | SM/13477 | New | Construction of Tube Well (300 MM x 200 MM x Depth 450 Mtr) for Feugram Water supply Scheme (T/W-I & II), Block- Nanoor, in Birbhum District by Bolpur Mechanical Division, P.H.Engineering Dte. | Assistant Engineer | Junior Engineer | ORD/000956/2024-2025 | 4532/BOL.MD | 20/12/2024 | 19/04/2025 | SATYAJIT GHOSH | 75.35 | 8.46 | 11.23 | 40
Total | [13 empty] | 598.23 | 13.2 | 2.21