## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Nalhati-II | Birbhum Division | Nawapara Piped Water Supply Scheme | SM/13479 | New | Preparation and submission of DPR for (Nawapara) Water Supply Scheme under Nalhati-II Development Block. | AE | JE2 | ORD/000758/2022-2023 | 231/AE/NSD | 21/04/2022 | 05/06/2022 | MS SOBHA AND CO | 4.6 | 4.6 | 100 | 100
2 | BIRBHUM | Nalhati-II | Birbhum Division | Nawapara Piped Water Supply Scheme | SM/13479 | New | Different works related to water supply scheme at NAWAPARA & PRASADPUR and its adjoining mouzas water supply scheme within NALHATI-II Block including supply of all labour & materials under Birbhum Division, PHE Dte. | AE | JE2 | ORD/000207/2023-2024 | 3257/BHM | 26/07/2023 | 26/04/2024 | MANASH GHOSH | 866.09 | 130.75 | 15.1 | 5
3 | BIRBHUM | Nalhati-II | Bolpur Mechanical | Nawapara Piped Water Supply Scheme | SM/13479 | New | Providing Electro-mechanical accessories and others for Nawpara PWSS at Nalhati - II Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000463/2023-2024 | 2137/Bol.MD | 25/08/2023 | 01/07/2025 | M. S. ENTERPRISE | 45.52 | 17 | 37.35 | 70
4 | BIRBHUM | Nalhati-II | Birbhum Division | Nawapara Piped Water Supply Scheme | SM/13479 | New | Material Requisition To Resource Division |  |  | RTOR000111/2023-2024 | 1502/BHM | 25/04/2023 | 25/04/2023 | Resource Division | 65.11 | 0 | 0 | 0
5 | BIRBHUM | Nalhati-II | Bolpur Mechanical | Nawapara Piped Water Supply Scheme | SM/13479 | New | Supply and Delivery of Volage correction device, Cetrifugal Pumping Machineries and allied accessories for Nawapara PWSS, (Block- Nalhati - II) under Bolpur Mechanical Division, PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000521/2024-2025 | 3780/BOL.MD | 12/09/2024 | 01/01/2025 | S.K.ELECTRICALS | 33.77 | 0 | 0 | 50
6 | BIRBHUM | Nalhati-II | Bolpur Mechanical | Nawapara Piped Water Supply Scheme | SM/13479 | New | WBSEDCL QUOTATION FOR NOAPARA P H .II WS SCHEME |  |  | BILL/01600/2023-2024 | BP-23-24-234 | 29/01/2024 | 29/01/2024 | WBSEDCL | 3.42 | 0 | 0 | 0
7 | BIRBHUM | Nalhati-II | Bolpur Mechanical | Nawapara Piped Water Supply Scheme | SM/13479 | New | WBSEDCL QUOTATION FOR NOAPARA WS SCHEME |  |  | BILL/01601/2023-2024 | BP-23-24-233 | 15/01/2024 | 15/01/2024 | WBSEDCL | 4.14 | 0 | 0 | 0
8 | BIRBHUM | Nalhati-II | Birbhum Division | Nawapara Piped Water Supply Scheme | SM/13479 | New | Extension of pipeline (DI & HDPE) with FHTC, Restoration of Roads including Augur boring along with supply of sluice valve with construction of valve chamber for Nawapara piped Water Supply Scheme under Nalhati Sub Division within Birbhum Division, P.H.E. Dte. | AE | JE2 | ORD/000193/2025-2026 | 2143/BHM | 19/08/2025 | 14/08/2026 | APORUPA CONSTRUCTION | 54.08 | 0 | 0 | 20
Total | [13 empty] | 1076.74 | 152.35 | 14.15