## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Mayureswar - I | Birbhum Division | Dabuk Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division | SM/13480 | New | Material Requisition To Resource Division |  |  | RTOR000113/2023-2024 | 1508/BHM | 26/04/2023 |  | Resource Division | 21.69 | 0 | 0 | 0
2 | BIRBHUM | Mayureswar - I | Birbhum Division | Dabuk Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division | SM/13480 | New | Continuation Work Order for Preparation & Submission of DPR for (Dabuk) Water Supply Scheme under Mayureswar-I Development Block. | AE | JE1 | ORD/000624/2022-2023 | 205/RSD | 13/06/2022 | 11/09/2022 | ENVIROTECH SOLUTIONS | 3.58 | 1.56 | 43.73 | 100
3 | BIRBHUM | Mayureswar - I | Bolpur Mechanical | Dabuk Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division | SM/13480 | New | Providing Electro-mechanical accessories and others for Dabuk PWSS at Mayureswar - I Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000523/2023-2024 | 2154/Bol.MD | 28/08/2023 | 27/10/2023 | M/S SAJAHAN CHOWDHURY | 44.02 | 6.45 | 14.66 | 30
4 | BIRBHUM | Mayureswar - I | Bolpur Mechanical | Dabuk Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division | SM/13480 | New | WBSEDCL QUOTATION FOR DABUK P H NO 1 WS SCHEME UNDER BOL MD PHE DTE |  |  | BILL/01439/2023-2024 | BP-23-24-177 | 07/12/2023 |  | WBSEDCL | 3.77 | 0 | 0 | 0
5 | BIRBHUM | Mayureswar - I | Birbhum Division | Dabuk Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division | SM/13480 | New | Material Requisition To Resource Division |  |  | RTOR000201/2023-2024 | 199/BHM | 22/01/2024 |  | Resource Division | 4.13 | 0 | 0 | 0
6 | BIRBHUM | Mayureswar - I | Bolpur Mechanical | Dabuk Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division | SM/13480 | New | Supply and Delivery of Pumping Machinery for Dabuk water supply scheme Block Mayureswar-I under Bolpur Mechanical Division PHE.Dte. | Assistant Engineer-III | Junior Engineer | ORD/001321/2023-2024 | 611./AE-III | 27/03/2024 | 03/04/2024 | M/S SAJAHAN CHOWDHURY | 1.49 | 0 | 0 | 0
7 | BIRBHUM | Mayureswar - I | Birbhum Division | Dabuk Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division | SM/13480 | New | Different works related to water supply scheme at DABUK & its adjoining mouzas water supply scheme within MAYURESWAR-I Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE,AE(HQ) | JE1 | ORD/000004/2023-2024 | 1083/BHM | 06/04/2023 | 01/01/2024 | ZEBA CONSTRUCTION | 270.01 | 33.33 | 12.34 | 60
8 | BIRBHUM | Mayureswar - I | Bolpur Mechanical | Dabuk Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division | SM/13480 | New | New service connection at Dabuk PH-II PWSS, Mayureswar -I Block, Under Bolpur Mechanical Division , P.H.E Dte. |  |  | BILL/00111/2024-2025 | BP-2024-2025-52 | 29/05/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.01 | 0 | 0 | null
Total | [13 empty] | 352.7 | 41.34 | 11.72