## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Nanoor | Birbhum Division | Charkalgram Piped Water Supply Scheme | SM/13481 | New | Material Requisition To Resource Division |  |  | RTOR000064/2023-2024 | 1470/BHM | 25/04/2023 |  | Resource Division | 26.63 | 0 | 0 | 0
2 | BIRBHUM | Nanoor | Birbhum Division | Charkalgram Piped Water Supply Scheme | SM/13481 | New | Continuation Work Order for "Preparation & Submission of Detail Project Report (DPR) for CHARKALGRAM Piped Water Supply Scheme under Nanoor Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte." (PART - B). | AE | JE4 | ORD/000735/2022-2023 | 310/BSD | 16/08/2022 | 12/02/2023 | RADIANT | 2.18 | 0.2 | 9.24 | 100
3 | BIRBHUM | Nanoor | Birbhum Division | Charkalgram Piped Water Supply Scheme | SM/13481 | New | Continuation Work Order for "Preparation & Submission of Detail Project Report (DPR) for CHARKALGRAM Piped Water Supply Scheme under Nanoor Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte." (PART - A) | AE | JE4 | ORD/000734/2022-2023 | 235/BSD | 15/06/2022 | 12/12/2022 | RADIANT | 4.94 | 2.57 | 51.95 | 100
4 | BIRBHUM | Nanoor | Central Drilling | Charkalgram Piped Water Supply Scheme | SM/13481 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 17/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
5 | BIRBHUM | Nanoor | Birbhum Division | Charkalgram Piped Water Supply Scheme | SM/13481 | New | Different works related to water supply scheme at CHARKALGRAM PIPED WATER SUPPLY SCHEME(TSM/016091) within NANOOR Block including supply of all labour & materials under Bolpur Sub-Division within Birbhum Division, PHE Dte. | Assistant Engineer | JE2 | ORD/000151/2024-2025 | 2608/BHM | 11/09/2024 | 11/09/2025 | GARGO TRADERS | 432.8 | 0 | 0 | 0
Total | [13 empty] | 21806.31 | 2.77 | 0.01