## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Bolpur Sriniketan | Birbhum Division | Monoharpur Piped Water Supply Scheme. | SM/13511 | New | Material Requisition To Resource Division |  |  | RTOR000089/2022-2023 | 1361/BHM | 24/04/2023 | 24/04/2023 | Resource Division | 16.8 | 0 | 0 | 0
2 | BIRBHUM | Bolpur Sriniketan | Bolpur Mechanical | Monoharpur Piped Water Supply Scheme. | SM/13511 | New | NEW SERVICE CONNECTION AT MONOHORPUR WATER SUPPLY SCHEME |  |  | BILL/00438/2024-2025 | BP-2024-25-141 | 06/08/2024 | 06/08/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 6.41 | 0 | 0 | 0
3 | BIRBHUM | Bolpur Sriniketan | Bolpur Mechanical | Monoharpur Piped Water Supply Scheme. | SM/13511 | New | ADDITIONAL QUOTATION FOR MONOHARPUR PWSS, BLOCK - BOLPUR SRINIKETAN DUE TO SOME CHANGES IN EXECUTED WORK UNDER SKN CCC. |  |  | BILL/01633/2024-2025 | BP-24-25-366 | 27/03/2025 | 27/03/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.4 | 0 | 0 | 0
4 | BIRBHUM | Bolpur Sriniketan | Central Drilling | Monoharpur Piped Water Supply Scheme. | SM/13511 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 85.01 | 0.4 | 11
5 | BIRBHUM | Bolpur Sriniketan | Birbhum Division | Monoharpur Piped Water Supply Scheme. | SM/13511 | New | Different works related to water supply scheme at MONOHARPUR, MOSTALA, RUPPUR & SALAN Piped Water Supply Scheme within BOLPUR-SRINIKETAN Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE,Assistant Engineer | JE4,JE_BLK_NANOOR | ORD/000398/2023-2024 | 4137/BHM | 18/10/2023 | 09/01/2026 | NAUTANDAS AND CO | 2897.79 | 0 | 0 | 10
Total | [13 empty] | 24261.17 | 85.01 | 0.35