## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Illambazar | Bolpur Mechanical | SHRICHANDRAPUR PIPED WATER SUPPLY SCHEME | SM/13516 | New | NEW SERVICE CONNECTION AT SHRICHNDRAPUR PWSS PH-I |  |  | BILL/00838/2024-2025 | BP-24-25-190 | 24/09/2024 | 24/09/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 6.57 | 0 | 0 | 0
2 | BIRBHUM | Illambazar | Bolpur Mechanical | SHRICHANDRAPUR PIPED WATER SUPPLY SCHEME | SM/13516 | New | Additional quotation for extra involvement of materials against application no - 5004294122 at Shrichandrapur PWSS, P/H- I under Illambazar CCC |  |  | BILL/01019/2024-2025 | BP-24-25-273 | 04/12/2024 | 04/12/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.54 | 0 | 0 | 0
3 | BIRBHUM | Illambazar | Bolpur Mechanical | SHRICHANDRAPUR PIPED WATER SUPPLY SCHEME | SM/13516 | New | NEW SERVICE CONNECTION FOR AT SHRICHANDRAPUR PWSS PH-II |  |  | BILL/00971/2024-2025 | BP-24-25-267 | 25/11/2024 | 25/11/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.22 | 0 | 0 | 0
4 | BIRBHUM | Illambazar | Birbhum Division | SHRICHANDRAPUR PIPED WATER SUPPLY SCHEME | SM/13516 | New | Different works related to water supply scheme at SHRICHANDRAPUR Piped Water Supply Scheme within Illambazar Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE | JE1 | ORD/000071/2023-2024 | 1345/BHM | 20/04/2023 | 28/07/2026 | RADHARANI ENTERPRISE | 165.15 | 41.63 | 25.21 | 5
5 | BIRBHUM | Illambazar | Central Drilling | SHRICHANDRAPUR PIPED WATER SUPPLY SCHEME | SM/13516 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 92.04 | 0.43 | 11
Total | [13 empty] | 21516.24 | 133.67 | 0.62