## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Dubrajpur | Birbhum Division | Khanpur piped water supply scheme. | SM/13539 | New | Material Requisition To Resource Division |  |  | RTOR000071/2022-2023 | 1393/BHM | 24/04/2023 | 24/04/2023 | Resource Division | 113.77 | 0 | 0 | 0
2 | BIRBHUM | Dubrajpur | Bolpur Mechanical | Khanpur piped water supply scheme. | SM/13539 | New | Supply, delivery and storage of different Electro-Mechanical accessories at Khanpur PWSS under Bolpur Mmechanical Division, PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000578/2024-2025 | 3849/BOL.MD | 18/09/2024 | 18/10/2024 | CINZANO | 31.2 | 0 | 0 | 0
3 | BIRBHUM | Dubrajpur | Bolpur Mechanical | Khanpur piped water supply scheme. | SM/13539 | New | Providing Electro-mechanical accessories and others for Khanpur and Adjoining moujas water supply scheme under Bolpur Mechanical Division PHE Dte., Block : Dubrajpur, Dist : Birbhum | Assistant Engineer-III | Junior Engineer | ORD/001047/2023-2024 | 07/BOL.MD | 03/01/2024 | 02/04/2024 | AHALYA ENGINEERING WORKS | 21.75 | 20.14 | 92.58 | 100
4 | BIRBHUM | Dubrajpur | Bolpur Mechanical | Khanpur piped water supply scheme. | SM/13539 | New | Supply Delivery & Installation of Electro-mechanical accessories at Khanpur & Adjoining moujas water supply scheme under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000899/2024-2025 | 4408/Bol.MD | 28/11/2024 | 12/01/2025 | AHALYA ENGINEERING WORKS | 16.93 | 7.86 | 46.43 | 100
5 | BIRBHUM | Dubrajpur | Bolpur Mechanical | Khanpur piped water supply scheme. | SM/13539 | New | Providing Electro-mechanical accessories and others for Khanpur & Adjoining moujas water supply scheme under Bolpur Mechanical Division PHE Dte., Block : Dubrajpur, Dist : Birbhum. | Assistant Engineer-III | Junior Engineer | ORD/000517/2024-2025 | 3763/Bol.MD | 12/09/2024 | 12/10/2024 | AHALYA ENGINEERING WORKS | 19.44 | 19.42 | 99.9 | 100
6 | BIRBHUM | Dubrajpur | Birbhum Division | Khanpur piped water supply scheme. | SM/13539 | New | Different works related to water supply scheme at PARULIA, KHANPUR & PADUMA and its adjoining mouzas water supply scheme within DUBRAJPUR Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE | JE,JE3 | ORD/000076/2023-2024 | 1425/BHM | 25/04/2023 | 01/01/2026 | BIPIN KUMAR SINGH | 2248.63 | 256.05 | 11.39 | 55
Total | [13 empty] | 2451.72 | 303.46 | 12.38