## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Illambazar | Birbhum Division | DELORA PIPED WATER SUPPLY SCHEME | SM/13600 | New | Material Requisition To Resource Division |  |  | RTOR000077/2023-2024 | 1459/BHM | 25/04/2023 | 25/04/2023 | Resource Division | 12.35 | 0 | 0 | 0
2 | BIRBHUM | Illambazar | Bolpur Mechanical | DELORA PIPED WATER SUPPLY SCHEME | SM/13600 | New | New Power Connection at Delora PWSS under Bolpur mechanical Division, PHE Dte. |  |  | BILL/00414/2024-2025 | BP-24-25-130 | 29/07/2024 | 29/07/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.84 | 0 | 0 | 0
3 | BIRBHUM | Illambazar | Birbhum Division | DELORA PIPED WATER SUPPLY SCHEME | SM/13600 | New | Different works related to water supply scheme at DELORA Piped Water Supply Scheme within ILLAMBAZAR Block including supply of all labour & materials under Bolpur Sub-Division within Birbhum Division, PHE Dte. | AE,Assistant Engineer | JE1 | ORD/000022/2023-2024 | 1192/BHM | 12/04/2023 | 29/03/2026 | M/S SANDIP CONSTRUCTION | 278.71 | 0 | 0 | 5
4 | BIRBHUM | Illambazar | Central Drilling | DELORA PIPED WATER SUPPLY SCHEME | SM/13600 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
Total | [13 empty] | 21633.67 | 0 | 0