## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Dubrajpur | Birbhum Division | Kukutia piped water supply scheme. | SM/13601 | New | Material Requisition To Resource Division |  |  | RTOR000076/2022-2023 | 1394/BHM | 24/04/2023 | 24/04/2023 | Resource Division | 67.88 | 0 | 0 | 0
2 | BIRBHUM | Dubrajpur | Bolpur Mechanical | Kukutia piped water supply scheme. | SM/13601 | New | Providing Electro-mechanical accessories and others for Kukutia & Adjoining moujas water supply scheme at Dubrajpur Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000936/2023-2024 | 3393/Bol.MD | 17/10/2023 | 15/01/2024 | S.K.ELECTRICALS | 52.82 | 8.54 | 16.16 | 60
3 | BIRBHUM | Dubrajpur | Birbhum Division | Kukutia piped water supply scheme. | SM/13601 | New | Material Requisition To Resource Division |  |  | RTOR000031/2024-2025 | 2487/BHM | 03/09/2024 | 03/09/2024 | Resource Division | 8.26 | 0 | 0 | 0
4 | BIRBHUM | Dubrajpur | Birbhum Division | Kukutia piped water supply scheme. | SM/13601 | New | Erection of Sign Board (900mm X 600mm) for demarcation of land at various places under Birbhum Division, PHE Dte. | AE,AE(HQ) | Estimator,JE | ORD/000458/2024-2025 | 3608/BHM | 31/12/2024 | 31/03/2025 | IMAGIN | 40.29 | 0 | 0 | 95
Total | [13 empty] | 169.26 | 8.54 | 5.04