## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Sainthia | Birbhum Division | NARAYANPUR PIPED WATER SUPPLY SCHEME. | SM/13625 | New | Material Requisition To Resource Division |  |  | RTOR000062/2022-2023 | 1421/BHM | 24/04/2023 |  | Resource Division | 68.68 | 0 | 0 | 0
2 | BIRBHUM | Sainthia | Bolpur Mechanical | NARAYANPUR PIPED WATER SUPPLY SCHEME. | SM/13625 | New | WBSEDCL QUOTATION FOR NARAYANPUR WS SCHEME |  |  | BILL/00701/2023-2024 | BP-2023-2024-57 | 02/08/2023 |  | WBSEDCL | 4.31 | 0 | 0 | 0
3 | BIRBHUM | Sainthia | Bolpur Mechanical | NARAYANPUR PIPED WATER SUPPLY SCHEME. | SM/13625 | New | WBSEDCL QUOTATION FOR NARAYAN PUR WS SCHEME |  |  | BILL/00702/2023-2024 | BP-2023-2024-58 | 02/08/2023 |  | WBSEDCL | 10.03 | 0 | 0 | 0
4 | BIRBHUM | Sainthia | Bolpur Mechanical | NARAYANPUR PIPED WATER SUPPLY SCHEME. | SM/13625 | New | Providing Electro-mechanical accessories and others for Narayanpur & Adjoining moujas water supply scheme at Sainthia Block under Bolpur Mechanical Division PHE Dte. | Driller in Charge | Junior Engineer | ORD/000777/2022-2023 | 314/Bol.MD | 24/03/2023 | 23/05/2023 | RAJIB COMPANY | 28.9 | 13.32 | 46.1 | 30
5 | BIRBHUM | Sainthia | Birbhum Division | NARAYANPUR PIPED WATER SUPPLY SCHEME. | SM/13625 | New | Construction of 5.90 m X 4.10 m Pump room/ Chlorine room with sanitary arrangements, 4.10 m X 3.50 m Pump house without sanitary arrangements, 250 CuM capacity O.H.R., Boundary wall, Soil Investigation, Land development, Rising main, Laying distribution, Approach Road and Providing functional household tap connection related to water supply scheme at NARAYANPUR & its adjoining mouzas wate supply scheme within Sainthia Block including supply of all labour & materials under BIRBHUM Division, PHE Dte | AE | JE3 | ORD/000125/2024-2025 | 2238/BHM | 13/08/2024 | 13/08/2025 | DILIP KUMAR MONDAL | 383.91 | 0 | 0 | 0
6 | BIRBHUM | Sainthia | Birbhum Division | NARAYANPUR PIPED WATER SUPPLY SCHEME. | SM/13625 | New | Material Requisition To Resource Division |  |  | RTOR000033/2024-2025 | 2488/BHM | 03/09/2024 |  | Resource Division | 9.52 | 0 | 0 | 0
Total | [13 empty] | 505.35 | 13.32 | 2.64