## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Murarai-II | Birbhum Division | Math Basori Piped Water Supply Scheme. | SM/13627 | New | Material Requisition To Resource Division |  |  | RTOR000088/2023-2024 | 1549/BHM | 26/04/2023 | 26/04/2023 | Resource Division | 18.63 | 0 | 0 | 0
2 | BIRBHUM | Murarai-II | Bolpur Mechanical | Math Basori Piped Water Supply Scheme. | SM/13627 | New | Quotation deposit for empowering Math Basuri Water Supply Scheme P/H -II in Paikar CCC under Bolpur Mechanical Division, PHE Dte |  |  | BILL/00116/2024-2025 | BP-2024-2025-47 | 29/05/2024 | 29/05/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.21 | 0 | 0 | 0
3 | BIRBHUM | Murarai-II | Bolpur Mechanical | Math Basori Piped Water Supply Scheme. | SM/13627 | New | Quotation deposit for empowering Math Basuri Water Supply Scheme P/H -I in Paikar CCC under Bolpur Mechanical Division, PHE Dte |  |  | BILL/00115/2024-2025 | BP-2024-2025-46 | 29/05/2024 | 29/05/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.03 | 0 | 0 | 0
4 | BIRBHUM | Murarai-II | Birbhum Division | Math Basori Piped Water Supply Scheme. | SM/13627 | New | Different works related to water supply scheme at Jijigram, Math Basori & Bilaspur and its adjoining mouzas water supply scheme within MURARAI-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE | JE3 | ORD/000191/2023-2024 | 3019/BHM | 14/07/2023 | 01/03/2026 | SUNIL RABI DAS | 1250.5 | 199.34 | 15.94 | 60
5 | BIRBHUM | Murarai-II | Bolpur Mechanical | Math Basori Piped Water Supply Scheme. | SM/13627 | New | Providing Electro-mechanical accessories and others for Math Basori PWSS at Murarai - II Block under Bolpur Mechanical Division PHE Dte. | Driller in Charge | Junior Engineer | ORD/000944/2023-2024 | 3305/BOL.MD | 29/09/2023 | 01/04/2025 | SUNIL RABIDAS | 28.78 | 18.11 | 62.92 | 50
Total | [13 empty] | 1306.14 | 217.45 | 16.65