## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Murarai-II | Birbhum Division | Math Basori Piped Water Supply Scheme. | SM/13627 | New | Material Requisition To Resource Division |  |  | RTOR000088/2023-2024 | 1549/BHM | 26/04/2023 | 26/04/2023 | Resource Division | 18.63 | 0 | 0 | 0
2 | BIRBHUM | Murarai-II | Bolpur Mechanical | Math Basori Piped Water Supply Scheme. | SM/13627 | New | Quotation deposit for empowering Math Basuri Water Supply Scheme P/H -II in Paikar CCC under Bolpur Mechanical Division, PHE Dte |  |  | BILL/00116/2024-2025 | BP-2024-2025-47 | 29/05/2024 | 29/05/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.21 | 0 | 0 | 0
3 | BIRBHUM | Murarai-II | Bolpur Mechanical | Math Basori Piped Water Supply Scheme. | SM/13627 | New | Quotation deposit for empowering Math Basuri Water Supply Scheme P/H -I in Paikar CCC under Bolpur Mechanical Division, PHE Dte |  |  | BILL/00115/2024-2025 | BP-2024-2025-46 | 29/05/2024 | 29/05/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.03 | 0 | 0 | 0
4 | BIRBHUM | Murarai-II | Birbhum Division | Math Basori Piped Water Supply Scheme. | SM/13627 | New | Different works related to water supply scheme at Jijigram, Math Basori & Bilaspur and its adjoining mouzas water supply scheme within MURARAI-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE | JE3 | ORD/000191/2023-2024 | 3019/BHM | 14/07/2023 | 01/03/2026 | SUNIL RABI DAS | 1250.5 | 199.34 | 15.94 | 60
5 | BIRBHUM | Murarai-II | Birbhum Division | Math Basori Piped Water Supply Scheme. | SM/13627 | New | Wall writing on smooth wall surface (preferably of Govt. premises/Boundary Wall) by cleaning the surface thoroughly, removing old paint, preparing with one coat good quality exterior primer and Two cost best quality exterior synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc. of multiple color as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Birbhum all completed as per direction of EIC. (Size- 8'-4') 2215 nos. village (2 nos. each) | AE | Estimator,JE | ORD/000492/2024-2025 | 203/BHM | 16/01/2025 | 16/04/2025 | IMAGIN | 67.84 | 0 | 0 | 100
6 | BIRBHUM | Murarai-II | Bolpur Mechanical | Math Basori Piped Water Supply Scheme. | SM/13627 | New | Providing Electro-mechanical accessories and others for Math Basori PWSS at Murarai - II Block under Bolpur Mechanical Division PHE Dte. | Driller in Charge | Junior Engineer | ORD/000944/2023-2024 | 3305/BOL.MD | 29/09/2023 | 01/04/2025 | SUNIL RABIDAS | 28.78 | 18.11 | 62.92 | 50
Total | [13 empty] | 1373.99 | 217.45 | 15.83