## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Sainthia | Central Drilling | Kurumsaha Piped Water Supply Scheme. | SM/13628 | New | PROVIDING DRILLING CREWS FOR CONSTRUCTION OF TUBE WELL BY DEPARTMENTAL RIG MACHINE IN KURUMSAHA PWSS (TW-I), BLOCK-SAINTHIA, BIRBHUM DISTRICT UNDER CDD, PHE DTE. |  |  | ORD/000417/2022-2023 | 398/CMSD-I | 05/08/2022 | 20/08/2022 | C.M. ENTERPRISE | 3.77 | 2.5 | 66.28 | 0
2 | BIRBHUM | Sainthia | Central Drilling | Kurumsaha Piped Water Supply Scheme. | SM/13628 | New | PROVIDING DRLLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM X 150 MTRS DEPTH) BY UTILISING DEPARTMENTAL MACHINERIES FOR Kurumsaha W/S SCHEME (TW-II), SAINTHIA BLOCK, UNDER BIRBHUM DISTRICT, CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000405/2022-2023 | 1428/CDD | 29/11/2022 | 29/12/2022 | C.M. ENTERPRISE | 10.49 | 9.15 | 87.23 | 0
3 | BIRBHUM | Sainthia | Central Drilling | Kurumsaha Piped Water Supply Scheme. | SM/13628 | New | PROVIDING TUBE WELL MATERIALS, CONFORMING TO IS: 12818:2010 WITH OTHER WORKS AT SITE FOR CONSTRUCTION OF TUBE WELL IN KURUMSAHA PWSS (TW-I), SAINTHIA BLOCK, BIRBHUM DISTRICT UNDER CDD, PHE DTE. |  |  | ORD/000415/2022-2023 | 382/CMSD-I | 05/08/2022 | 20/08/2022 | C.M. ENTERPRISE | 4.18 | 3.79 | 90.77 | 0
4 | BIRBHUM | Sainthia | Central Drilling | Kurumsaha Piped Water Supply Scheme. | SM/13628 | New | SUPPLY & DELIVERY OF CONSUMBLES WITH OTHER WORKS AT SITE FOR CONSTTRUCTION OF TUBE WELL IN KURUMSAHA PWSS (TW-I), BLOCK-SAINTHIA, BIRBHUM DISTRICT UNDER CDD, PHE DTE. |  |  | ORD/000416/2022-2023 | 390/CMSD-I | 05/08/2022 | 20/08/2022 | C.M. ENTERPRISE | 2.66 | 2.64 | 99.38 | 0
5 | BIRBHUM | Sainthia | Birbhum Division | Kurumsaha Piped Water Supply Scheme. | SM/13628 | New | Material Requisition To Resource Division |  |  | RTOR000051/2022-2023 | 1366/BHM | 24/04/2023 | 24/04/2023 | Resource Division | 19.69 | 0 | 0 | 0
6 | BIRBHUM | Sainthia | Bolpur Mechanical | Kurumsaha Piped Water Supply Scheme. | SM/13628 | New | WBSEDCL QUOTATION FOR KURUMSAHA P.H.NO.I |  |  | BILL/00707/2023-2024 | BP-2023-2024-63 | 02/08/2023 | 02/08/2023 | WBSEDCL | 3.85 | 0 | 0 | 0
7 | BIRBHUM | Sainthia | Bolpur Mechanical | Kurumsaha Piped Water Supply Scheme. | SM/13628 | New | wbsedcl quotation for kurumsaha p.h.no.ii ws scheme |  |  | BILL/00716/2023-2024 | BP-23-24-70 | 09/08/2023 | 09/08/2023 | WBSEDCL | 3.91 | 0 | 0 | 0
8 | BIRBHUM | Sainthia | Bolpur Mechanical | Kurumsaha Piped Water Supply Scheme. | SM/13628 | New | Providing Electro-mechanical accessories and others for Kurumsaha & Adjoining moujas water supply scheme at Sainthia Block under Bolpur Mechanical Division PHE Dte. | Driller in Charge | Junior Engineer | ORD/000418/2023-2024 | 2090/Bol.MD | 22/08/2023 | 01/07/2025 | MITRA ENTERPRISE | 28.04 | 23.99 | 85.53 | 80
9 | BIRBHUM | Sainthia | Birbhum Division | Kurumsaha Piped Water Supply Scheme. | SM/13628 | New | Different works related to water supply scheme at DERPUR, KURUMSAHA & MATIARA and its adjoining mouzas water supply scheme within SAINTHIA Block including supply of all labour & materials under Birbhum Division, PHE Dte. | AE | JE | ORD/000056/2023-2024 | 1245/BHM | 17/04/2023 | 26/03/2026 | BRAHMA CONSTRUCTION COMPANY | 978.83 | 154.45 | 15.78 | 65
Total | [13 empty] | 1055.41 | 196.52 | 18.62