## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Mayureswar-I | Birbhum Division | Sonj Piped Water Supply Scheme under Mayureswar-I within Birbhum Division | SM/13630 | New | Material Requisition To Resource Division |  |  | RTOR000072/2023-2024 | 1465/BHM | 25/04/2023 | 25/04/2023 | Resource Division | 51.71 | 0 | 0 | 0
2 | BIRBHUM | Mayureswar-I | Bolpur Mechanical | Sonj Piped Water Supply Scheme under Mayureswar-I within Birbhum Division | SM/13630 | New | Providing Electro-mechanical accessories and others for Sonj PWSS at Mayureswar - I Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000725/2023-2024 | 3472/Bol.MD | 07/11/2023 | 06/01/2024 | HINDOL ROY | 57.29 | 0 | 0 | 40
3 | BIRBHUM | Mayureswar-I | Bolpur Mechanical | Sonj Piped Water Supply Scheme under Mayureswar-I within Birbhum Division | SM/13630 | New | Supply and Installation of Submersible pumping machineries and other electromechanical equipments at Sonj PWSS under Mayureswar Block-I in the Dist of Birbhum under Bolpur Mechanical Division,P.H.E.Dte. | Assistant Engineer-III | Junior Engineer | ORD/001218/2023-2024 | 403/Bol.MD | 07/03/2024 | 21/04/2024 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 24.55 | 0 | 0 | 80
4 | BIRBHUM | Mayureswar-I | Birbhum Division | Sonj Piped Water Supply Scheme under Mayureswar-I within Birbhum Division | SM/13630 | New | Continuation Work Order for Preparation & Submission of DPR for (Sonj) Water Supply Scheme (Part-B) under Mayureswar-I Development Block. | AE | JE3 | ORD/000833/2022-2023 | 428/RSD | 09/11/2022 | 07/02/2023 | ENVIROTECH SOLUTIONS | 2.5 | 0 | 0 | 100
5 | BIRBHUM | Mayureswar-I | Birbhum Division | Sonj Piped Water Supply Scheme under Mayureswar-I within Birbhum Division | SM/13630 | New | Continuation Work Order for Preparation & Submission of DPR for (Sonj) Water Supply Scheme (Part-A) under Mayureswar-I Development Block. | AE | JE3 | ORD/000832/2022-2023 | 327/RSD | 08/09/2022 | 07/12/2022 | ENVIROTECH SOLUTIONS | 3.29 | 0 | 0 | 100
6 | BIRBHUM | Mayureswar-I | Birbhum Division | Sonj Piped Water Supply Scheme under Mayureswar-I within Birbhum Division | SM/13630 | New | Material Requisition To Resource Division |  |  | RTOR000207/2023-2024 | 207/BHM | 22/01/2024 | 22/01/2024 | Resource Division | 6.16 | 0 | 0 | 0
7 | BIRBHUM | Mayureswar-I | Bolpur Mechanical | Sonj Piped Water Supply Scheme under Mayureswar-I within Birbhum Division | SM/13630 | New | WBSEDCL QUOTATION FOR SONJ W/S SCHEME PH-3 |  |  | BILL/02466/2023-2024 | BP-24-25-01 | 09/04/2024 | 09/04/2024 | WBSEDCL | 2.8 | 0 | 0 | 0
8 | BIRBHUM | Mayureswar-I | Bolpur Mechanical | Sonj Piped Water Supply Scheme under Mayureswar-I within Birbhum Division | SM/13630 | New | WBSEDCL QUOTATION FOR SONJ W/S SCHEME PH-2 |  |  | BILL/02463/2023-2024 | BP-24-25-02 | 09/04/2024 | 09/04/2024 | WBSEDCL | 3.18 | 0 | 0 | 0
9 | BIRBHUM | Mayureswar-I | Bolpur Mechanical | Sonj Piped Water Supply Scheme under Mayureswar-I within Birbhum Division | SM/13630 | New | WBSEDCL QUOTATION FOR SONJPIPED WS SCHEME PH NO.I |  |  | BILL/01882/2023-2024 | BP-23-24-283 | 22/02/2024 | 22/02/2024 | WBSEDCL | 3.74 | 0 | 0 | 0
10 | BIRBHUM | Mayureswar-I | Birbhum Division | Sonj Piped Water Supply Scheme under Mayureswar-I within Birbhum Division | SM/13630 | New | Different works related to water supply scheme at LACHHIATOR, DAKSHINGRAM, SONJ & SHIBGRAM and its adjoining mouzas water supply scheme within MAYURESWAR-I Block including supply of all labour & materials under Birbhum Division, PHE Dte. | AE | JE2 | ORD/000385/2023-2024 | 4142/BHM | 19/10/2023 | 01/01/2026 | B RAI CONSTRUCTION COMPANY | 2003.84 | 0 | 0 | 60
Total | [13 empty] | 2159.05 | 0 | 0