## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Dubrajpur | Bolpur Mechanical | Gokrui Piped Water Supply Scheme. | SM/13631 | New | Providing Electro-mechanical accessories and others for Gokrui & Adjoining moujas water supply scheme at Dubrajpur Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000578/2023-2024 | 3382/Bol.MD | 16/10/2023 | 14/01/2024 | SATYAJIT GHOSH | 51.95 | 0 | 0 | 0
2 | BIRBHUM | Dubrajpur | Birbhum Division | Gokrui Piped Water Supply Scheme. | SM/13631 | New | Material Requisition To Resource Division |  |  | RTOR000075/2022-2023 | 1392/BHM | 24/04/2023 | 24/04/2023 | Resource Division | 54.79 | 0 | 0 | 0
3 | BIRBHUM | Dubrajpur | Birbhum Division | Gokrui Piped Water Supply Scheme. | SM/13631 | New | Construction of 5.90 m X 4.10 m Pump room/ Chlorine room with sanitary arrangements, 4.10 m X 3.50 m Pump house without sanitary arrangements, 8.00 m X 8.00 m Pump room/ Chlorine room with sanitary arrangements, 100 CuM capacity O.H.R. 100 CuM CWR, Boundary wall, Soil Investigation, Land development, Rising main, Laying distribution, Approach road and Providing functional household tap connection related to water supply scheme at GOKRUI & its adjoining mouzas water supply scheme within Dubrajpur Block including supply of all labour & materials under BIRBHUM Division, PHE Dte | AE | JE1,JE3 | ORD/000115/2024-2025 | 2181/BHM | 06/08/2024 | 06/08/2025 | SARAFAT KHAN | 232.15 | 0 | 0 | 0
4 | BIRBHUM | Dubrajpur | Birbhum Division | Gokrui Piped Water Supply Scheme. | SM/13631 | New | Material Requisition To Resource Division |  |  | RTOR000030/2024-2025 | 2453/BHM | 30/08/2024 | 30/08/2024 | Resource Division | 5.09 | 0 | 0 | 0
Total | [13 empty] | 343.97 | 0 | 0