## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Dubrajpur | Bolpur Mechanical | Gokrui Piped Water Supply Scheme. | SM/13631 | New | Providing Electro-mechanical accessories and others for Gokrui & Adjoining moujas water supply scheme at Dubrajpur Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000578/2023-2024 | 3382/Bol.MD | 16/10/2023 | 14/01/2024 | SATYAJIT GHOSH | 51.95 | 0 | 0 | 0
2 | BIRBHUM | Dubrajpur | Birbhum Division | Gokrui Piped Water Supply Scheme. | SM/13631 | New | Material Requisition To Resource Division |  |  | RTOR000075/2022-2023 | 1392/BHM | 24/04/2023 | 24/04/2023 | Resource Division | 54.79 | 0 | 0 | 0
3 | BIRBHUM | Dubrajpur | Birbhum Division | Gokrui Piped Water Supply Scheme. | SM/13631 | New | Material Requisition To Resource Division |  |  | RTOR000030/2024-2025 | 2453/BHM | 30/08/2024 | 30/08/2024 | Resource Division | 5.09 | 0 | 0 | 0
Total | [13 empty] | 111.83 | 0 | 0