## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Dubrajpur | Bolpur Mechanical | Majuria Piped Water Supply Scheme. | SM/13632 | New | Providing Electro-mechanical accessories and others for Majuri & Adjoining moujas water supply scheme at Dubrajpur Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000579/2023-2024 | 3383/Bol.MD | 16/10/2023 | 14/01/2024 | SATYAJIT GHOSH | 72.19 | 0 | 0 | 0
2 | BIRBHUM | Dubrajpur | Birbhum Division | Majuria Piped Water Supply Scheme. | SM/13632 | New | Material Requisition To Resource Division |  |  | RTOR000078/2022-2023 | 1397/BHM | 24/04/2023 | 24/04/2023 | Resource Division | 195.98 | 0 | 0 | 0
3 | BIRBHUM | Dubrajpur | Birbhum Division | Majuria Piped Water Supply Scheme. | SM/13632 | New | Material Requisition To Resource Division |  |  | RTOR000049/2024-2025 | 3268/BHM | 02/12/2024 | 02/12/2024 | Resource Division | 15.42 | 0 | 0 | 0
4 | BIRBHUM | Dubrajpur | Birbhum Division | Majuria Piped Water Supply Scheme. | SM/13632 | New | Sinking of 250 X 200 mm Dia and 125 m deep tubewell, Construction of 5.90 m X 4.10 m Pump room/ Chlorine room with sanitary arrangements, 4.10 m X 3.50 m Pump house without sanitary arrangements, 8.00 m X 8.00 m Pump room/ Chlorine room with sanitary arrangements, 350 CuM capacity O.H.R. and respectively, 150 CuM CWR, Boundary wall, Soil Investigation, Land development, Rising main, Laying distribution, Approach Road and Providing functional household tap connection related to MAJURIA & its adjoining mouzas water supply scheme within Dubrajpur Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE | JE,JE3 | ORD/000188/2024-2025 | 2770/BHM | 30/09/2024 | 30/09/2025 | JALPRAVAHIKA PVT. LTD. | 609.71 | 0 | 0 | 20
Total | [13 empty] | 893.3 | 0 | 0