## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Illambazar | Birbhum Division | CHUNPALASHI PIPED WATER SUPPLY SCHEME | SM/13637 | New | Material Requisition To Resource Division |  |  | RTOR000080/2023-2024 | 1533/BHM | 26/04/2023 | 26/04/2023 | Resource Division | 47.92 | 0 | 0 | 0
2 | BIRBHUM | Illambazar | Birbhum Division | CHUNPALASHI PIPED WATER SUPPLY SCHEME | SM/13637 | New | Continuation Work Order for "Preparation & Submission of Detail Project Report (DPR) for CHUNPALASHI Piped Water Supply Scheme within command area of Illambazar Development Block under Bolpur Sub-Division within Birbhum Division, PHE Dte.". | AE | JE1 | ORD/001145/2021-2022 | 121/BSD | 31/03/2022 | 29/06/2022 | M/S R DUTTA & CO. | 4.29 | 4.21 | 98.23 | 100
3 | BIRBHUM | Illambazar | Birbhum Division | CHUNPALASHI PIPED WATER SUPPLY SCHEME | SM/13637 | New | Different works related to water supply scheme at MATIKONA, NOHONA, SHIRSHA & CHUNPALASHI Piped Water Supply Scheme within ILLAMBAZAR Block including supply of all labour & materials under Bolpur Sub-Division within Birbhum Division, PHE Dte. | AE | JE1 | ORD/000278/2023-2024 | 3598/BHM | 21/08/2023 | 24/12/2026 | BIPIN KUMAR SINGH | 2395.67 | 0 | 0 | 4
Total | [13 empty] | 2447.88 | 4.21 | 0.17