## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Rampurhat-I | Birbhum Division | Chakpara piped water supply scheme. | SM/13638 | New | Different works related to water supply scheme at CHAKPARA & its adjoining mouzas water supply scheme within Rampurhat-I Block including supply of all labour & materials under Birbhum Division, PHE Dte. (2nd Call) | AE | JE1,JE3 | ORD/000405/2023-2024 | 4188/BHM | 01/11/2023 | 01/03/2026 | NABIN DEBNATH | 471.71 | 59.42 | 12.6 | 75
2 | BIRBHUM | Rampurhat-I | Bolpur Mechanical | Chakpara piped water supply scheme. | SM/13638 | New | Providing Electro-mechanical accessories and others for Chakpara & Adjoining PWSS at Rampurhat - I Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000917/2023-2024 | 3525/Bol.MD | 29/11/2023 | 27/12/2025 | M. S. ENTERPRISE | 39.06 | 31.25 | 80 | 60
3 | BIRBHUM | Rampurhat-I | Birbhum Division | Chakpara piped water supply scheme. | SM/13638 | New | Material Requisition To Resource Division |  |  | RTOR000138/2023-2024 | 1558/BHM | 26/04/2023 | 26/04/2023 | Resource Division | 32.34 | 0 | 0 | 0
4 | BIRBHUM | Rampurhat-I | Birbhum Division | Chakpara piped water supply scheme. | SM/13638 | New | Material Requisition To Resource Division |  |  | RTOR000220/2023-2024 | 228/BHM | 24/01/2024 | 24/01/2024 | Resource Division | 3.08 | 0 | 0 | 0
5 | BIRBHUM | Rampurhat-I | Bolpur Mechanical | Chakpara piped water supply scheme. | SM/13638 | New | Quotation for Chakpara PWSS P/H no-2 ( block: Rampurhat I) |  |  | BILL/00076/2024-2025 | BP-2024-2025-22 | 20/05/2024 | 20/05/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.83 | 0 | 0 | 0
6 | BIRBHUM | Rampurhat-I | Bolpur Mechanical | Chakpara piped water supply scheme. | SM/13638 | New | Quotation for new service connection at Chakpara PWSS P/H -1 ( Block : Rampurhat -1) |  |  | BILL/00077/2024-2025 | BP-2024-2025-24 | 20/05/2024 | 20/05/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.09 | 0 | 0 | 0
7 | BIRBHUM | Rampurhat-I | Birbhum Division | Chakpara piped water supply scheme. | SM/13638 | New | Construction of 5.90 m X 4.10 m Pump room/ Chlorine room with sanitary arrangements, Boundary wall related to water supply scheme at Chakpara Piped Water Supply Scheme within Rampurhat-I Block including supply of all labour & materials under Birbhum Division, PHE Dte. | AE | JE1 | ORD/000063/2025-2026 | 1584/BHM | 02/06/2025 | 31/08/2025 | ABUL HASNATH | 26.1 | 0 | 0 | 0
8 | BIRBHUM | Rampurhat-I | Bolpur Mechanical | Chakpara piped water supply scheme. | SM/13638 | New | Supply and Delivery of Sub-Mersible Pumping Machineries for Chakpara water supply scheme (Block- Rampurhat - I) Pump House No - I, II & III under Bolpur Mechanical Division, PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/001092/2024-2025 | 245./AE-III | 30/01/2025 | 06/02/2025 | M. S. ENTERPRISE | 2.69 | 0 | 0 | 100
Total | [13 empty] | 583.91 | 90.67 | 15.53