## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Bolpur Sriniketan | Birbhum Division | Ikshudhara piped water supply scheme. | SM/13639 | New | Material Requisition To Resource Division |  |  | RTOR000086/2022-2023 | 1358/BHM | 24/04/2023 |  | Resource Division | 119 | 0 | 0 | 0
2 | BIRBHUM | Bolpur Sriniketan | Bolpur Mechanical | Ikshudhara piped water supply scheme. | SM/13639 | New | Providing Electro-mechanical accessories and others for Ikshudhara & Adjoining moujas water supply scheme at Bolpur Sriniketan Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000482/2023-2024 | 2239/BOL.MD. | 13/09/2023 | 12/12/2023 | QUAZI NOZRUL ISLAM | 80.69 | 19.07 | 23.63 | 50
3 | BIRBHUM | Bolpur Sriniketan | Bolpur Mechanical | Ikshudhara piped water supply scheme. | SM/13639 | New | WBSEDCL QUOTATION FOR Ikshudhara piped water supply scheme. |  |  | BILL/01592/2023-2024 | BP-23-24-220 | 15/01/2024 |  | WBSEDCL | 6.17 | 0 | 0 | 0
4 | BIRBHUM | Bolpur Sriniketan | Bolpur Mechanical | Ikshudhara piped water supply scheme. | SM/13639 | New | WBSEDCL QUOTATION FOR Ikshudhara piped water supply scheme. |  |  | BILL/01592/2023-2024 | BP-23-24-220 | 15/01/2024 |  | WBSEDCL | 6.17 | 0 | 0 | 0
5 | BIRBHUM | Bolpur Sriniketan | Birbhum Division | Ikshudhara piped water supply scheme. | SM/13639 | New | Different works related to water supply scheme at IKSHUDHARA, KANKALITALA, KASBA & KENDANGAL Piped Water Supply Scheme within BOLPUR-SRINIKETAN Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE | JE4 | ORD/000402/2023-2024 | 4139/BHM | 18/10/2023 | 14/07/2024 | M/S TAPAS KUMAR CHAKRABORTY | 2684.99 | 169.12 | 6.3 | 25
6 | BIRBHUM | Bolpur Sriniketan | Central Drilling | Ikshudhara piped water supply scheme. | SM/13639 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 17/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
Total | [13 empty] | 24236.77 | 188.19 | 0.78