## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Bolpur Sriniketan | Birbhum Division | Ikshudhara piped water supply scheme. | SM/13639 | New | Material Requisition To Resource Division |  |  | RTOR000086/2022-2023 | 1358/BHM | 24/04/2023 | 24/04/2023 | Resource Division | 119 | 0 | 0 | 0
2 | BIRBHUM | Bolpur Sriniketan | Bolpur Mechanical | Ikshudhara piped water supply scheme. | SM/13639 | New | Supply and delivery of Starter and other materials for ikshudhara water supply scheme under Bolpur Mechanical Division PHE Dte. | Assistant Engineer (HQ) | Junior Engineer | ORD/000544/2024-2025 | 3803/BOL.MD | 12/09/2024 | 02/10/2024 | STANDARD ELECTRICALS | 6.54 | 6.54 | 100 | 100
3 | BIRBHUM | Bolpur Sriniketan | Bolpur Mechanical | Ikshudhara piped water supply scheme. | SM/13639 | New | Supply & delivery of submersible cable accessories at ikshudhara Piped water supply scheme under Bolpur Mechanical Division, PHE Dte. | Assistant Engineer (HQ) | Junior Engineer | ORD/000557/2024-2025 | 3821/BOL.MD | 18/09/2024 | 08/10/2024 | MITRA ENTERPRISE | 2.8 | 0 | 0 | 100
4 | BIRBHUM | Bolpur Sriniketan | Bolpur Mechanical | Ikshudhara piped water supply scheme. | SM/13639 | New | Supply and delivery of chlorinator dosing pump for ikshudhara Water Supply Project under Bolpur Mechanical Divn. P.H.E. Dte. | Assistant Engineer (HQ) | Junior Engineer | ORD/000549/2024-2025 | 3818/BOL.MD | 18/09/2024 | 08/10/2024 | M/S. UTTAM KUMAR CHATTERJEE | 3.24 | 0.96 | 29.68 | 100
5 | BIRBHUM | Bolpur Sriniketan | Bolpur Mechanical | Ikshudhara piped water supply scheme. | SM/13639 | New | WBSEDCL QUOTATION FOR Ikshudhara piped water supply scheme. |  |  | BILL/01592/2023-2024 | BP-23-24-220 | 15/01/2024 | 15/01/2024 | WBSEDCL | 6.17 | 0 | 0 | 0
6 | BIRBHUM | Bolpur Sriniketan | Birbhum Division | Ikshudhara piped water supply scheme. | SM/13639 | New | Different works related to water supply scheme at IKSHUDHARA, KANKALITALA, KASBA & KENDANGAL Piped Water Supply Scheme within BOLPUR-SRINIKETAN Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE | JE4 | ORD/000402/2023-2024 | 4139/BHM | 18/10/2023 | 01/01/2027 | M/S TAPAS KUMAR CHAKRABORTY | 2684.99 | 434.22 | 16.17 | 60
7 | BIRBHUM | Bolpur Sriniketan | Bolpur Mechanical | Ikshudhara piped water supply scheme. | SM/13639 | New | Hiring of vehicle for the office of the Executive Engineer, Bolpur Mechanical Division, P.H.E.Dte. | Assistant Engineer (HQ) | Junior Engineer | ORD/001233/2024-2025 | 4216/BOL.MD | 23/10/2024 | 11/05/2025 | SATYAJIT GHOSH | 0.57 | 1.51 | 264.84 | 100
8 | BIRBHUM | Bolpur Sriniketan | Bolpur Mechanical | Ikshudhara piped water supply scheme. | SM/13639 | New | Supply & delivery of Starter and other materials for Different water supply scheme in ikshudhara under Bolpur Mechanical Division PHE Dte. | Assistant Engineer (HQ) | Junior Engineer | ORD/000554/2024-2025 | 3823/BOL.MD | 18/09/2024 | 08/10/2024 | QUAZI NOZRUL ISLAM | 2.65 | 2.65 | 100 | 100
Total | [13 empty] | 2825.94 | 445.88 | 15.78