## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Rampurhat-I | Birbhum Division | Kanaipur piped water supply scheme. | SM/13640 | New | Continuation Work Order for Preparation & Submission of DPR for (Kanaipur) Water Supply Scheme under Mayureswar-I Development Block. | AE | JE1 | ORD/000628/2022-2023 | 220/RSD | 21/06/2022 | 19/09/2022 | ENVIROTECH SOLUTIONS | 4.93 | 4.77 | 96.59 | 100
2 | BIRBHUM | Rampurhat-I | Birbhum Division | Kanaipur piped water supply scheme. | SM/13640 | New | Material Requisition To Resource Division |  |  | RTOR000105/2023-2024 | 1513/BHM | 26/04/2023 | 26/04/2023 | Resource Division | 57.41 | 0 | 0 | 0
3 | BIRBHUM | Rampurhat-I | Birbhum Division | Kanaipur piped water supply scheme. | SM/13640 | New | Material Requisition To Resource Division |  |  | RTOR000218/2023-2024 | 235/BHM | 24/01/2024 | 24/01/2024 | Resource Division | 9.27 | 0 | 0 | 0
4 | BIRBHUM | Rampurhat-I | Bolpur Mechanical | Kanaipur piped water supply scheme. | SM/13640 | New | New service connection at Kanaipur PH-II PWSS ,Mayureswar- I , under Bolpur mechanical Division, P.H.E Dte. |  |  | BILL/00109/2024-2025 | BP-2024-2025-48 | 29/05/2024 | 29/05/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.27 | 0 | 0 | 0
5 | BIRBHUM | Rampurhat-I | Bolpur Mechanical | Kanaipur piped water supply scheme. | SM/13640 | New | New service connection at Kanaipur PH-I PWSS , Mayureswar-I Block under Bolpur Mechanical Division,P.H.E Dte. |  |  | BILL/00110/2024-2025 | BP-2024-2025-49 | 29/05/2024 | 29/05/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 7.8 | 0 | 0 | 0
6 | BIRBHUM | Rampurhat-I | Birbhum Division | Kanaipur piped water supply scheme. | SM/13640 | New | Different works related to water supply scheme at KANAIPUR & its adjoining mouzas water supply scheme within RAMPURHAT-I Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE | JE1,JE3 | ORD/000206/2023-2024 | 3251/BHM | 26/07/2023 | 30/06/2025 | BENGAL ENGINEERING | 564.7 | 138.47 | 24.52 | 30
7 | BIRBHUM | Rampurhat-I | Bolpur Mechanical | Kanaipur piped water supply scheme. | SM/13640 | New | Providing Electro-mechanical accessories (H/L and L/L) and others for Kanaipur & Adjoining moujas water supply scheme within Rampurhat - I Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000526/2023-2024 | 2168/Bol.MD | 31/08/2023 | 31/03/2025 | SATYAJIT GHOSH | 77.69 | 36.94 | 47.55 | 48
Total | [13 empty] | 727.07 | 180.18 | 24.78