## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Illambazar | Birbhum Division | Kayera Water Supply Scheme | SM/13641 | New | Material Requisition To Resource Division |  |  | RTOR000081/2023-2024 | 1489/BHM | 25/04/2023 | 25/04/2023 | Resource Division | 11.95 | 0 | 0 | 0
2 | BIRBHUM | Illambazar | Birbhum Division | Kayera Water Supply Scheme | SM/13641 | New | Preparation & Submission of Detail Project Report (DPR) for KAYERA Water Supply Scheme & SHRICHANDRAPUR Piped Water Supply Scheme under Illambazar Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte. | AE | JE1 | ORD/001118/2021-2022 | 99/BSD | 15/03/2022 | 13/06/2022 | M/S R DUTTA & CO. | 4.65 | 4.29 | 92.33 | 100
3 | BIRBHUM | Illambazar | Bolpur Mechanical | Kayera Water Supply Scheme | SM/13641 | New | New Service connection of Kayera PWSS P/H- I (Block- Illambazar) |  |  | BILL/00135/2024-2025 | BP-2024-2025-54 | 05/06/2024 | 05/06/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.83 | 0 | 0 | 0
4 | BIRBHUM | Illambazar | Bolpur Mechanical | Kayera Water Supply Scheme | SM/13641 | New | Additional Quotation for extra involvement of materials against consumer ID 503652443 at Koyra site under Illambazar ccc |  |  | BILL/00970/2024-2025 | BP-2024-25-266 | 25/11/2024 | 25/11/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.54 | 0 | 0 | 0
5 | BIRBHUM | Illambazar | Birbhum Division | Kayera Water Supply Scheme | SM/13641 | New | Different works related to water supply scheme at KAYERA Piped Water Supply Scheme within ILLAMBAZAR Block including supply of all labour & materials under Bolpur Sub-Division within Birbhum Division, PHE Dte. | AE | JE1 | ORD/000019/2023-2024 | 1214/BHM | 12/04/2023 | 12/01/2024 | USHA ENTERPRISE | 334.74 | 52.23 | 15.6 | 5
6 | BIRBHUM | Illambazar | Birbhum Division | Kayera Water Supply Scheme | SM/13641 | New | Hiring of 01 (One) no. vehicle for the Office of the Assistant Engineer, Bolpur Sub-Division, P.H.E Dte. under Birbhum Division, P.H.E Dte. For the period of 01.04.2024 to 30.09.2024. | AE | JE3 | ORD/000704/2023-2024 | 269/BSD | 15/03/2024 | 15/09/2024 | SK AKRAM HOSSAIN | 0.86 | 2.39 | 277.37 | 100
7 | BIRBHUM | Illambazar | Central Drilling | Kayera Water Supply Scheme | SM/13641 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 57.6 | 0.27 | 11
Total | [13 empty] | 21698.32 | 116.51 | 0.54